L: Leader
P: Participant
## Document
Document data	Data name	Data remark	© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Project identification	Document title	Detailed description of project management
C Jousselin	Document author	Project accountable
V 2,0	Document version	Version of the document
12/10/25	Document version date	Date of this version
ProjectToy	Project name	Contract name of the project
Motor racing circuit	Project sub-name	Sub-name of the project
Copyright		Attribution — You must give appropriate credit , provide a link to the license, and indicate if changes were made. You may do so in any reasonable manner, but not in any way that suggests the licensor endorses you or your use.
		NonCommercial — You may not use the material for commercial purposes.
MÉTHODE JET		NoDerivatives — If you remix, transform, or build upon the material, you may not distribute the modified material.
https://meta-projet.eu	<= Méthode JET link

## Description
Description of ProjectToy			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
During a meeting between Leo and Jules, Leo expressed his desire to have a small wooden car track. Jules replied that he knew Christian, who would be able to carry out this project with him. Jules and Christian drew up an offer for Leo, who accepted it, and the three men signed a contract. Leo agreed to pay €500 for this project and to receive it in three months.
As Jules and Christian only wanted to take responsibility for their own work, their bid was structured as a consortium (60% CW, 40% EM) Jules called on Jean, Vincent, Paul and Thomas to carry out the “civil (CW)” part of the project, and Christian called on Alain, Jacques, Xavier and Yves to carry out the “electromechanical (EM)” part.
Jules set up an integrated JV with Jean, Vincent, Paul and Thomas. On his side, Christian set up an integrated JV with Alain, Jacques, Xavier, and Yves.
All members of the project decide to work for free, just for fun.
The object of this project should be similar to the photos below:

## Actor graph
ProjectToy		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0					The real actors of this meta project
Actor graph					Client / Leo					The purpose of this document is to illustrate the meta project “MÉTHODE JET“ using a simple project, highlighting different representations of the fundamentals of a project. / Of course, due to the simplicity of the project, certain dimensions and/or matrices do not seem necessary; however, they would be essential in a more complex project; and even additional representations.
				Contract					&
				Which one of you ?
	Media				Civil Works JV / Jules / Consortium / Leader					E&M JV / Christian / Consortium / Deputy					1 Who would like to understand the “Méthode JET” through an example ? / (only an illustrative project to understand the concepts of project dimension &, matrix) / 2 Who would like to learn how to create project matrices using a spreadsheet ? / (very simple: pivot tables, named data zone, simple copy macro, WBS Database & MATRIX Database) / 3 Who is interested in a motor racing circuit ? / (this is not the right place)				 /  / 
				JV agreement					JV agreement
				Consortium agreement

	CW Project management / Jules		Civil Engineering / Jean		Bridge sub-group / Vincent		Road sub-group / Thomas		Building sub-group / Paul		EM Project management / Christian		EM Engineering / Jacques		Car sub-group / Alain		Power supply sub-group / Xavier		Track sub-group / Yves

			Economic flow
			Possible economic flow
			Agreement
			Contract
			Operational link
				Suppliers		Sub-contractors				Engineering school fab lab

## Dimensions
Project dimensions		Contrat Creative Commons BY-NC-ND 4.0	© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Dimension code	Dimension name	Dimension attribute
CWBS	Contractual work breakdown structure	Project-specific contract
PBS	Product breakdown structure	Usually specific to a project, but can also be a generic type related to the company's standard products.
GBS	Geographical breakdown structure	Project-specific location/zone of products to be delivered
FBS	Function breakdown structure	Project-specific Function to be delivered
WP	Work package breakdown structure	Project-specific tasks management level, which can be derived from a standard structure within the company
OBS	Organisation breakdown structure	Project-specific organisation structure, which can be derived from a standard structure within the company
TBS	Time breakdown structure	Project-specific time management structure
PIBS	Price breakdown structure	Project-specific price management structure
COBS	Cost breakdown structure	Project-specific cost management structure
RBS	Resources work breakdown structure	Project-specific resource management structure
CAP	Organisational capabilities	Project-specific organisational capability
RIBS	Risk & opportunity breakdown structure	Project-specific uncertainty management framework

ABStypes	Type of activity breakdown structure	Generic type related to the company's main activities (company expertise, all company activities)
RBStypes	Type of resource breakdown structure	Generic type linked to the company's main resources
CBStypes	Type of cost breakdown structure	Generic type linked to the company's accounting system
ROLEtypes	Type of role breakdown structure	Very classical types of roles (RACI)
Calendar	Project calendar	Project-specific calendar considering local holidays and non-working days

## Matrix views
Matrix views			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Matrix code	Matrix name	Matrice attribute
CWBS view	Project client view	CWBS x (WBS ; PBS ; GBS ; ABStypes ; WP ; OBS ; ROLEtypes ; WBSremark)
WP view	Project work packages	WP x (CWBS ; PBS ; GBS ; ABStypes ; WBS ; OBS ; ROLEtypes ; WBSremark)
WBS view	Project tasks	WBS x (CWBS ; PBS ; GBS ; ABStypes ; WP ; OBS ; ROLEtypes ; WBSremark)
PBS view	Project products	PBS x (CWBS ; WBS ; GBS ; ABStypes ; WP ; OBS ; ROLEtypes ; WBSremark)
GBS view	Geographical view	GBS x (CWBS ; PBS ; WBS ; ABStypes ; WP ; OBS ; ROLEtypes ; WBSremark)
OBS view	Organisation view	OBS x (CWBS ; PBS ; GBS ; ABStypes ; WP ; WBS ; ROLEtypes ; WBSremark)

Time schedule	Planning	TBS x Calendar
Time–distance diagram	Geo-temporal planning	GBS x Calendar
TBS x WP view	Time assignment	TBS x WP
SWOT view	Capabilities and risk analysis	CAP x RIBS
RESOURCE view	Resource assignment	WP x RBS
PRODUCT INTERFACE view	Product interface	PBS x PBS
FUNCTION view	Function allocation	PBS x FBS

## Tools
Project tools	These tools are not ‘real’ project tools; they are only there to demonstrate how simple it is to implement the "Méthode Jet".		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Tool code	Tool name	Tool attribute
Input WBS tool	Method for declaring each WBS element with the necessary attributes.	CWBS, PBS, GBS, ABStypes, WP, OBS, ROLEtypes, WBS attribute
Input INTERFACE tool	Method for declaring each interface element in one dimension.	Every dimension, interface attribute. Example: PBS x PBS
Input MATRIX tool	Method for declaring each element of a two-dimensional array.	Every dimensions, matrix attribute. Example: PBS x FBS

## CWBS
Contract	Granularity of contract management : Contract dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
CWBS code	CWBS name	CWBS attribute	Level
@	All parts of the contract		1
CW	Civil works		1
CWR	Roads	6 m x 0,3 m	2
CWR1	Straight road elements	All identical	3
CWR2	Curve road elements	All identical	3
CWR3	Bridge	1 long bridge	3
CWB	Grandstand building	2 buildings	2
EME	Electro-mechanical equipments		1
CAR	Cars	2 cars	2
PS	Power supply	1 power pack	2
HSC	Handheld speed controller	2 controllers	2
ENG	Engineering		1
MGM	Project Management		1
CON	Other contractual obligations		1
TS	Time schedule	3 months	1
PP	Project price	500 €	1
PCW	Civil works price (50% on 45th day)	300 €	2
PEM	Electro-mechanical equipments price (50% on 45th day)	200 €	2
SP	Spares		1
SPMO	Motor	1 motor for car	2
SPSC	Handheld speed controller	1 controller	2
SPSR	Straight road	1 straight road element	2
SPCR	Curve road	1 curve road element	2
DOC	Contractual documentation		1
DUM	User manual	1 copy	2
DAI	Assembly instruction	1 copy	2
MR	Monthly report		2
WR	Warranty	1 year	1
OPT	OPTION	No option defined	1
AMD	CONTRACT AMENDMENT	No contract amendment yet	1

## PBS
Product	Granularity of product management : Product dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
PBS code	PBS name	PBS attribute	Level
@	All products		1
@1	USER MANUAL	#	2
@2	ASSEMBLY INSTRUCTIONS	#	2
1	CARS	2 cars	1
11	MOTOR	#	2
12	CAR GUIDANCE SYSTEM	#	2
13	BODYSHELL AND FITTINGS	#	2
14	PNEUMATICS	#	2
15	CAR SPARES	#	2
151	MOTOR SPARES	1 motor for car	3
2	POWER SUPPLY		1
21	HANDHELD SPEED CONTROLLER	2 controllers	2
22	POWER SUPPLY PACK	1 power supply pack	2
23	POWER SUPPLY CABLES	#	2
24	PS SPARES	#	2
241	HANDHELD SPEED CONTROLLER SPARES	1 controller	3
3	TRACK INFRASTRUCTURE		1
31	ELECTRICAL STRIPS	2*6 meters (including bridge)	2
4	BUILDING		1
41	GRANDSTAND BUILDING	2 buildings	2
5	ROAD	6 meters including bridge	1
51	STRAIGHT ROAD	All identical	2
52	CURVE ROAD	All identical	2
53	ROAD SPARES	#	2
531	STRAIGHT ROAD SPARES	1 straight road	3
532	CURVE ROAD SPARES	1 curve road	3
6	BRIDGE	1 bridge	1

## GBS
Localisation			Granularity of geographical management : Geographical dimension			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Position (m)			GBS code	GBS name	GBS attribute	Level
			@	Project (All localisation)		1
			#	Project (No localisation)		1
			SR	All STRAIGHT ROAD SECTIONS		1
			CR	All CURVE ROAD SECTIONS		1
			GB	All GRANDSTAND BUILDING SECTIONS		1
6	CR05	TEST ROAD
5,9
5,8
5,7
5,6
5,5			CR05	CURVE ROADS 05	Position: 5.4 Length: 0.6 m	2
5,4	CR04
5,3
5,2
5,1
5
4,9			CR04	CURVE ROADS 04	Position: 4.8 Length: 0.6 m	2
4,8	SR03
4,7
4,6
4,5
4,4			SR03	STRAIGHT ROAD 03	Position: 4.3 Length: 0.5 m	2
4,3	CR03
4,2
4,1			TR	E&M TEST ROAD	Position: 4,0 Length: 2 m	1
4		PS	PS	POWER SUPPLY PACK CONNEXION	Position: 4.0	1
3,9
3,8			CR03	CURVE ROADS 03	Position: 3.7 Length: 0.6 m	2
3,7	SR02	GB02
3,6
3,5
3,4			SR02	STRAIGHT ROAD 02	Position: 3.2 Length: 0.5 m	2
3,3			GB02	GRANDSTAND BUILDING 02	Position: 3.2 Length: 0.5 m	2
3,2	CR02
3,1
3
2,9
2,8
2,7			CR02	CURVE ROADS 02	Position: 2.6 Length: 0.6 m	2
2,6	BR01
2,5
2,4
2,3
2,2
2,1
2
1,9
1,8
1,7
1,6
1,5
1,4
1,3
1,2			BR01	LONG BRIDGE	Position: 1.1 Length: 1.5 m	1
1,1	CR01
1
0,9
0,8
0,7
0,6			CR01	CURVE ROADS 01	Position: 0.5 Length: 0.6 m	2
0,5	SR01	GB01
0,4
0,3
0,2			SR01	STRAIGHT ROAD 01	Position: 0 Length: 0.5 m	2
0,1			GB01	GRANDSTAND BUILDING 01	Position: 0 Length: 0.5 m	2

## FBS
Function	Granularity of function management : Function dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
FBS code	FBS name	FBS attribute	Level
Mobility	Mobility function	Mobility function	1
Motorisation	Mobility on roads	Electrical function	2
Speed control	Energy control	Dynamic function	2
Guidance	Direction control	Mechanical function	2
Adherence	Stability through adhesion	Mechanical function	2
Energy	Energy function	Energy function	1
Power capture	Transformer	Electrical collector function	2
AC/DC	Rectifier	Rectifier function	2
Distribution on roads	Energy distribution	On road electrical distribution function	2

## OBS
Organisation	Granularity of organisation management : Organisation dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
OBS code	OBS name	OBS attribute	Level
CLT	Client	Sole proprietorship	1
CON	Consortium	Consortium	1
CWG	Civil Works JV	Integrated joint venture	2
PMC	CW Project management	Sole proprietorship	3
ENC	Civil Engineering	Sole proprietorship	3
BRG	Bridge sub-group	Sole proprietorship	3
ROAD	Road sub-group	Sole proprietorship	3
BLG	Building sub-group	Sole proprietorship	3
EMG	E&M JV	Integrated joint venture	2
PME	EM Project management	Sole proprietorship	3
ENE	EM Engineering	Sole proprietorship	3
CAG	Car sub-group	Sole proprietorship	3
PSG	Power supply sub-group	Sole proprietorship	3
TRG	Track sub-group	Sole proprietorship	3

## WP
Work package	Granularity of management : Management dimension		Expected cost progress			Expected physical progress			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
WP code	WP name	WP attribute (Organisation owner)	End of month 1	End of month 2	End of month 3	End of month 1	End of month 2	End of month 3	Physical progress criteria
CON-PM	CON Project management (only workload = free)	CON	0 %	0 %	0 %	33 %	66 %	100 %	Time spent/total or PM document ratio.
CW-PM	CW Project management (only workload = free)	CWG	0 %	0 %	0 %	33 %	66 %	100 %	Time spent/total or PM document ratio.
CW-EN	CW Engineering (only workload)	ENC	0 %	0 %	0 %	66 %	95 %	100 %	Design documents published/expected.
CW-BRO	CW Road and bridge	BRG	5 %	90 %	100 %	10 %	85 %	100 %	Number of metres of road/bridge constructed/total.
CW-BLD	CW buildings	BLG	5 %	100 %	100 %	10 %	75 %	100 %	Number of floors built/total.
CW-WAR	CW warranty provisions	CWG	0 %	0 %	0 %	0 %	0 %	0 %	Cost spent/budget.
EM-PM	EM Project management (only workload = free)	EMG	0 %	0 %	0 %	33 %	77 %	100 %	Time spent/total or PM document ratio.
EM-EN	EM Engineering (only workload = free)	ENE	0 %	0 %	0 %	33 %	66 %	100 %	Design documents published/expected.
EM-CAR	EM Cars	CAG	5 %	80 %	100 %	10 %	50 %	100 %	Percentage of cars manufactured/total.
EM-PSTR	EM Power supply and tracks	PSG	5 %	90 %	100 %	10 %	85 %	100 %	Percentage of PS equipment manufactured/total.
EM-WAR	EM warranty provisions	EMG	0 %	0 %	0 %	0 %	0 %	0 %	Cost spent/budget.

## PIBS
Price	Granularity of price management : Price dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
PIBS code	PIBS name	PIBS attribute	Level
PP	Project price	500 €	1
PP	Project invoices	0 €	1
PCW	Civil works price including warranty & spares	300 €	2
PCW-INV	CW invoices (50% on 45th day)	0 €	2
PEM	Electro-mechanical price including warranty & spares	200 €	2
PEM-INV	EM invoices (50% on 45th day)	0 €	2
PADJ	Price adjustment formulas	0 €	2
PADJ-INV	EPADJ invoices	0 €	2

## COBS
Cost	Granularity of cost management : Cost dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
COBS code	COBS name	COBS attribute	Level
CONMAR	CON project margin (0 because Consortium)	0,00 €	1
CWMAR	CW project margin (0 by decision, if remaining => in warranty provision)	0,00 €	1
EMMAR	EM project margin (0 by decision, if remaining => in warranty provision)	0,00 €	1
CON-PM	CON Project management : WP budget estimate and actual cost (0 by decision)	0,00 €	1
PRJ-B	Project budget estimate	500,00 €	1
PRJ-A	Project actual cost	0,00 €	1
CCW-B	Civil works budget estimate (including spares)	300,00 €	2
CCW-A	Civil works actual cost (including spares)	0,00 €	2
CW-PM-B	CW Project management : WP budget estimate	0,00 €	3
CW-PM-A	CW Project management : WP actual cost	0,00 €	3
CW-EN-B	CW Engineering : WP budget estimate	0,00 €	3
CW-EN-A	CW Engineering : WP actual cost	0,00 €	3
CW-BRO-B	CW Road and bridge : WP budget estimate	175,00 €	3
CW-BRO-A	CW Road and bridge : WP actual cost	0,00 €	3
CW-BLD-B	CW buildings : WP budget estimate	110,00 €	3
CW-BLD-A	CW buildings : WP actual cost	0,00 €	3
CW-WAR-B	CW warranty provisions : WP budget estimate	15,00 €	3
CW-WAR-A	CW warranty provisions : WP actual cost	0,00 €	3
CEM-B	Electro-mechanical budget estimate (including spares)	200,00 €	2
CEM-A	Electro-mechanical actual cost (including spares)	0,00 €	2
EM-PM-B	EM Project management : WP budget estimate	0,00 €	3
EM-PM-A	EM Project management : WP actual cost	0,00 €	3
EM-EN-B	EM Engineering : WP budget estimate	0,00 €	3
EM-EN-A	EM Engineering : WP actual cost	0,00 €	3
EM-CAR-B	EM Cars : WP budget estimate	90,00 €	3
EM-CAR-A	EM Cars : WP actual cost	0,00 €	3
EM-PSTR-B	EM Power supply and tracks : WP budget estimate	100,00 €	3
EM-PSTR-A	EM Power supply and tracks : WP actual cost	0,00 €	3
EM-WAR-B	EM warranty provisions : WP budget estimate	10,00 €	3
EM-WAR-A	EM warranty provisions : WP actual cost	0,00 €	3

## TBS
Time	Granularity of time management : Time dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
TBS code	TBS name	TBS Target or physical progress	Level
MS	Contract master schedule	Contractual target	1
MS01	Contract signature	T0	2
MS02	Monthly report	Every 30 days	2
MS03	Delivery	T0 + 89 days.	2
MS04	Commissioning	T0 + 85-89 days.	2
MS05	Acceptance	T0 + 90 days.	2
MS06	Warranty period	1 year after acceptance date.	2
PMS	Project master schedule	Physical progress	1
PMS-M	Milestones		2
PMS-M01	Project charter issue	100,00 %	3
PMS-M02	Assignment of the core team	0,00 %	3
PMS-M03	Consortium launch meeting	0,00 %	3
PMS-M04	Project consortium management plan first issue	0,00 %	3
PMS-M05	Development management plan first issue	0,00 %	3
PMS-M06	Interface management plan first issue	0,00 %	3
PMS-M07	Production/installation management plan first issue	0,00 %	3
PMS-M08	Testing/commissioning management plan first issue	0,00 %	3
PMS-M09	Progress meeting	0,00 %	3
PMS-M10	Design frozen	0,00 %	3
PMS-M11	Sourcing completed	0,00 %	3
PMS-M12	End of building installation	0,00 %	3
PMS-M13	End of roads installation	0,00 %	3
PMS-M14	End of track installation	0,00 %	3
PMS-M15	Delivery of all cars	0,00 %	3
PMS-M16	Delivery of all PS equipments	0,00 %	3
PMS-M17	End of integration test	0,00 %	3
PMS-M18	End of pre-commissioning	0,00 %	3
PMS-M19	End of commissioning	0,00 %	3
PMS-M20	Client acceptance date	0,00 %	3
PMS-M21	Invoices	0,00 %	3
PMS-P	Phases		2
PMS-P01	Launch	0,00 %	3
PMS-P02	Design	0,00 %	3
PMS-P03	Sourcing	0,00 %	3
PMS-P04	Production/installation	0,00 %	3
PMS-P05	Testing	0,00 %	3
PMS-P06	Pre-commissioning	0,00 %	3
PMS-P07	Commissioning	0,00 %	3
PMS-P08	Acceptance	0,00 %	3
PMS-P09	Warranty	0,00 %	3
MS-CW	CW group master schedule	For CW project management	1
MS-CW-M	CW Milestones	Showing the interface milestones with EM	2
MS-CW-M01	Project CW group management plan first issue	0,00 %	3
MS-CW-M02	CW latest installation	0,00 %	3
MS-CW-WBS	CW WBS schedule	For CW task management	2
CW-(@-@)-M	CW project management	0,00 %	3
CW-(@-@)-D	CW engineering	0,00 %	3
CWB-(41-GB)-M	Building management	0,00 %	3
CWB-(41-GB)-D	Building design	0,00 %	3
CWB-(41-GB)-S	Building supply chain	0,00 %	3
CWB-(41-GB)-I	Building installation	0,00 %	3
CWR1-(51-SR)-M	Straight road management	0,00 %	3
CWR1-(51-SR)-D	Straight road design	0,00 %	3
CWR1-(51-SR)-S	Straight road supply chain	0,00 %	3
CWR1-(51-SR)-I	Straight road installation	0,00 %	3
CWR2-(52-CR)-M	Curve road management	0,00 %	3
CWR2-(52-CR)-D	Curve road design	0,00 %	3
CWR2-(52-CR)-S	Curve road supply chain	0,00 %	3
CWR2-(52-CR)-I	Curve road installation	0,00 %	3
CWR3-(6-BR01)-M	Bridge management	0,00 %	3
CWR3-(6-BR01)-D	Bridge design	0,00 %	3
CWR3-(6-BR01)-S	Bridge supply chain	0,00 %	3
CWR3-(6-BR01)-I	Bridge installation	0,00 %	3
DAI-(@2-#)-D	Writing the assembly instructions	0,00 %	3
SPCR-(532-CR)-P	Delivery of curve road spare parts	0,00 %	3
SPSR-(531-SR)-P	Delivery of straight road spare parts	0,00 %	3
MS-EM	EM group master schedule	For EM project management	1
MS-EM-M	EM Milestones	Showing the interface milestones with CW	2
MS-EM-M01	Project EM group management plan first issue	0,00 %	3
MS-EM-M02	EM latest production	0,00 %	3
MS-EM-WBS	EM WBS schedule	For EM task management	2
EME-(@-@)-M	E&M project management	0,00 %	3
EME-(@-@)-D	E&M engineering	0,00 %	3
CAR-(1-#)-M	Car management	0,00 %	3
CAR-(1-#)-D	Car design	0,00 %	3
CAR-(1-#)-S	Car supply chain	0,00 %	3
CAR-(1-#)-P	Car production	0,00 %	3
CAR-(1-#)-T	Car testing	0,00 %	3
CAR-(1-#)-C	Car commissioning	0,00 %	3
PS-(2-PS)-M	Power supply management	0,00 %	3
PS-(2-PS)-D	Power supply design	0,00 %	3
PS-(2-PS)-S	Power supply supply chain	0,00 %	3
HSC-(21-PS)-P	Handheld speed controller production	0,00 %	3
HSC-(21-PS)-T	Handheld speed controller testing	0,00 %	3
HSC-(21-PS)-C	Handheld speed controller commissioning	0,00 %	3
PS-(22-PS)-P	PS pack production	0,00 %	3
PS-(22-PS)-T	PS pack testing	0,00 %	3
PS-(22-PS)-C	PS pack commissioning	0,00 %	3
PS-(23-PS)-P	PS cables production	0,00 %	3
PS-(23-PS)-T	PS cables testing	0,00 %	3
PS-(3-@)-M	Track management	0,00 %	3
PS-(3-@)-D	Track design	0,00 %	3
PS-(3-@)-S	Track supply chain	0,00 %	3
PS-(3-@)-I	Track installation	0,00 %	3
PS-(3-@)-T	Track testing	0,00 %	3
PS-(3-@)-C	Track commissioning	0,00 %	3
ENG-(@-@)-C	Project commissioning	0,00 %	3
DUM-(@1-#)-D	Writing the user manual	0,00 %	3
SPSC-(241-PS)-P	Delivery of handheld speed controller spare parts	0,00 %	3
SPMO-(151-#)-S	Delivery of motor spare parts	0,00 %	3

## RBS
Resource	Granularity of resource management : Dimension of resources		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
RBS	Resource type	Contact attributes	Tel
Alain	H	Alain@projecttoy.eu	0601020304
Christian	H	Christian@projecttoy.eu	0601020305
Jacques	H	Jacques@projecttoy.eu	0601020306
Jean	H	Jean@projecttoy.eu	0601020307
Jules	H	Jules@projecttoy.eu	0601020308
Leo	H	Leo@projecttoy.eu	0601020309
Paul	H	Paul@projecttoy.eu	0601020310
Thomas	H	Thomas@projecttoy.eu	0601020311
Vincent	H	Vincent@projecttoy.eu	0601020312
Xavier	H	Xavier@projecttoy.eu	0601020313
Yves	H	Yves@projecttoy.eu	0601020314
CW tools	M	Vincent’ tools	Vincent’ home
EM tools	M	Xavier’ tools	Xavier’ home
WP budget (€)	B	See COBS dimension

## CAP
Capabilities	Organisational capabilities		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
CAP type	CAP name	CAP attribute measures
Strength	1 Willingness to work for free.	Promoting individuals (e.g., video presentation on social media of each project member).
Strength	2 Every member of the team is passionate about their field of work.	Promote the presentation of each individual piece of work within the project team.
Strength	3 Other strength to define	Enhancement measures to define
Weakness	1 The members of the project team did not know each other.	Organise a team-building session (for example, after work).
Weakness	2 There are two juniors in the team.	Create a pairing between a junior and a senior member of the team.
Weakness	3 There are no women on the team. We are losing creativity and open-mindedness.	Promote the project to attract female members (for example, if there are no female candidates in engineering, perhaps a female candidate in communications?).
Weakness	4 Other weakness to define	Attenuating measures to define

## RIBS
Risk and opportunity	Granularity of risk and opportunity management : Risk dimension		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
RIBS code	RIBS name	RIBS attribute measures
Risk / Threat	1 Xavier's 3D printer is unavailable or out of order.	Have a plan B ready, for example with a Fab Lab at an engineering school.
Risk / Threat	2 Vincent's laser cutter is unavailable or out of order.	Have a plan B ready, for example with a Fab Lab at an engineering school.
Risk / Threat	3 Other risk to be define	Mitigation measures to be define
Opportunity	1 Once the project has been delivered, another identical order may arrive, this time with a profit.	To increase the chances of success, make a video about the progress of the project to promote it. Then post it on social media.
Opportunity	2 Sponsoring the project	Prospect automotive and other companies to try to obtain subsidies by adding advertisements to the project.
Opportunity	3 Other opportunity to be define	Improvement measures to be define

## ABStypes
Activity type	Granularity of activity management types : Dimension of types of activities		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
ABS code	ABS name	ABS attribute	Level
@	Project (All activities)	All types of activities (M+D+S+P+T+I+C+L+W)	1
M	Project Management	All Project Management type of activities	1
D	Design	All Design type of activities	1
S	Supply Chain Management	All Supply Chain Management type of activities	1
P	Production	All Production type of activities	1
T	Testing	All Testing type of activities	1
I	Site Installation	All Site Installation type of activities	1
L	Logistic Support	All Logistic Support type of activities	1
C	Commissioning	All Commissioning type of activities	1
W	Warranty	All Warranty type of activities	1

## RBStypes
Ressource type	Granularity of resource management types : Dimension of types of resource		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
RBS types	Name	Remarks	Level
H	Human	Workforce	1
M	Material	Equipment and materials	1
I	Immaterial	Including software, licenses, royalties, etc.	1
B	Budget	Initial budget	1

## KPI
Relevance	Relevance criteria for the project (axes of meaning)		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
KPI code	KPI Name	KPI attribute	Level
TimeKPI	Physical progress	Physical weighting of the progress of work packages (physical progress/expected physical progress at that time).	1
CostKPI	Cost progress	Weighting of costs related to the progress of work packages (actual cost/expected cost progress at that time).	1
ClientKPI	Client satisfaction indicator	Measure progress against customer expectations (qualitative indicator or, in the case of numerous tests or partial acceptance, the ratio achieved/planned).	1

## ROLEtypes
Role type	Granularity of responsibility management types : Dimension of types of responsibilities		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
Role code	Role name	Role attribute	Level
A	Accountable	The sole person responsible for approving and validating the task. The buck stops here.	1
R	Responsible	The person or persons who carry out the task or objective. They are the “executors.”	2
C	Consulted	Individuals whose expertise or opinion is required before the task is completed or approved.	3
I	Informed	People who need to be kept up to date on progress or decisions, without being directly involved in carrying out the task.	4

## CBStypes
Cost type	Granularity of cost management types : Dimension of types of costs		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
CBS code	CBS name	CBS attribute	Level
C1	Material	Type for material supply	1
C2	Sub-contracted Work	Type for sub-contract	1
C3	Works Labour	Type for internal labour	1
C4	Other costs	Type for other costs	1
C5	Contingencies	Type for contingencies	1

## Calendar
Calendar
Month 1					Month 2					Month 3
1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	+ 1 year

## CWBS view
CWBS view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

PBS Name	- tout -
GBS Name	- tout -
ABS Name	- tout -

Compter - OBS code				OBS code	OBS Name
				BLG	BRG	CAG	CWG	EMG	ENC	ENE	PMC	PME	PSG	ROAD	TRG
CWBS code	CWBS Name	CWBS Attribute	WP code	Building sub-group	Bridge sub-group	Car sub-group	Civil Works JV	E&M JV	Civil Engineering	EM Engineering	CW Project management	EM Project management	Power supply sub-group	Road sub-group	Track sub-group
CAR	Cars	2 cars	EM-CAR			6
CW	Civil works	0	CW-EN					1	1
			CW-PM					1	1
CWB	Grandstand building	2 buildings	CW-BLD	4
CWR1	Straight road elements	All identical	CW-BRO		1					4
CWR2	Curve road elements	All identical	CW-BRO		1					4
CWR3	Bridge	1 long bridge	CW-BRO		4
DAI	Assembly instruction	1 copy	CW-EN					1
DUM	User manual	1 copy	EM-EN					1
EME	Electro-mechanical equipments	0	EM-EN					1	1
			EM-PM					1	1
ENG	Engineering	0	EM-EN					2	2
HSC	Handheld speed controller	2 controllers	EM-PSTR					3
MGM	Project Management	0	CON-PM				1	1
MR	Monthly report	0	CON-PM					1
PS	Power supply	1 power pack	EM-PSTR					9		6
SPCR	Curve road	1 curve road element	CW-BRO		1
SPMO	Motor	1 motor for car	EM-CAR			1
SPSC	Handheld speed controller	1 controller	EM-PSTR					1
SPSR	Straight road	1 straight road element	CW-BRO		1

## WP view
WP view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

		0
CWBS Name	- tout -
PBS Name	- tout -
GBS Name	- tout -
ABS Name	- tout -

Compter - ROLE code						ROLE code
WP code	WP Name	WP Attribute	OBS code	OBS Name	WBS code	R	A	C	I
CON-PM	CON Project management (only workload = free)	CON	CWG	Civil Works JV	MGM-(@-@)-M		1
			EMG	E&M JV	MGM-(@-@)-M	1
			PME	EM Project management	MR-(@-#)-M	1
CW-BLD	CW buildings	BLG	BLG	Building sub-group	CWB-(41-GB)-D		1
					CWB-(41-GB)-I		1
					CWB-(41-GB)-M		1
					CWB-(41-GB)-S		1
CW-BRO	CW Road and bridge	BRG	BRG	Bridge sub-group	CWR1-(51-SR)-M		1
					CWR2-(52-CR)-M		1
					CWR3-(6-BR01)-D		1
					CWR3-(6-BR01)-I		1
					CWR3-(6-BR01)-M		1
					CWR3-(6-BR01)-S		1
					SPCR-(532-CR)-P		1
					SPSR-(531-SR)-P		1
			ROAD	Road sub-group	CWR1-(51-SR)-D	1
					CWR1-(51-SR)-I	1
					CWR1-(51-SR)-M	1
					CWR1-(51-SR)-S	1
					CWR2-(52-CR)-D	1
					CWR2-(52-CR)-I	1
					CWR2-(52-CR)-M	1
					CWR2-(52-CR)-S	1
CW-EN	CW Engineering (only workload)	ENC	ENC	Civil Engineering	CW-(@-@)-D		1
					DAI-(@2-#)-D		1
			ENE	EM Engineering	CW-(@-@)-D				1
CW-PM	CW Project management (only workload = free)	CWG	PMC	CW Project management	CW-(@-@)-M		1
			PME	EM Project management	CW-(@-@)-M				1
EM-CAR	EM Cars	CAG	CAG	Car sub-group	CAR-(1-#)-C		1
					CAR-(1-#)-D		1
					CAR-(1-#)-M		1
					CAR-(1-#)-P		1
					CAR-(1-#)-S		1
					CAR-(1-#)-T		1
					SPMO-(151-#)-S		1
EM-EN	EM Engineering (only workload = free)	ENE	ENC	Civil Engineering	EME-(@-@)-D				1
					ENG-(@-@)-C			1
					ENG-(@-@)-D			1
			ENE	EM Engineering	DUM-(@1-#)-D		1
					EME-(@-@)-D		1
					ENG-(@-@)-C		1
					ENG-(@-@)-D		1
EM-PM	EM Project management (only workload = free)	EMG	PMC	CW Project management	EME-(@-@)-M				1
			PME	EM Project management	EME-(@-@)-M		1
EM-PSTR	EM Power supply and tracks	PSG	PSG	Power supply sub-group	HSC-(21-PS)-C		1
					HSC-(21-PS)-P		1
					HSC-(21-PS)-T		1
					PS-(2-PS)-D		1
					PS-(2-PS)-M		1
					PS-(2-PS)-S		1
					PS-(22-PS)-C		1
					PS-(22-PS)-P		1
					PS-(22-PS)-T		1
					PS-(23-PS)-P		1
					PS-(23-PS)-T		1
					PS-(3-@)-M		1
					SPSC-(241-PS)-P		1
			TRG	Track sub-group	PS-(3-@)-C	1
					PS-(3-@)-D	1
					PS-(3-@)-I	1
					PS-(3-@)-M	1
					PS-(3-@)-S	1
					PS-(3-@)-T	1

## WBS view
WBS view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

CWBS Name	- tout -
GBS Name	- tout -
WP code	- tout -

Compter - OBS code					OBS code
WBS code	PBS Name	ABS Name	ROLE code	WBS remark	BLG	BRG	CAG	CWG	EMG	ENC	ENE	PMC	PME	PSG	ROAD	TRG
CAR-(1-#)-C	CARS	Commissioning	A	Car commissioning			1
CAR-(1-#)-D	CARS	Design	A	Car design			1
CAR-(1-#)-M	CARS	Project Management	A	Car management			1
CAR-(1-#)-P	CARS	Production	A	Car production			1
CAR-(1-#)-S	CARS	Supply Chain Management	A	Car supply chain			1
CAR-(1-#)-T	CARS	Testing	A	Car testing			1
CW-(@-@)-D	All products	Design	A	CW engineering					1
			I	CW engineering					1
CW-(@-@)-M	All products	Project Management	A	CW project management					1
			I	CW project management					1
CWB-(41-GB)-D	GRANDSTAND BUILDING	Design	A	Building design	1
CWB-(41-GB)-I	GRANDSTAND BUILDING	Site Installation	A	Building installation	1
CWB-(41-GB)-M	GRANDSTAND BUILDING	Project Management	A	Building management	1
CWB-(41-GB)-S	GRANDSTAND BUILDING	Supply Chain Management	A	Building supply chain	1
CWR1-(51-SR)-D	STRAIGHT ROAD	Design	R	Straight road design					1
CWR1-(51-SR)-I	STRAIGHT ROAD	Site Installation	R	Straight road installation					1
CWR1-(51-SR)-M	STRAIGHT ROAD	Project Management	A	Straight road management		1
			R	Straight road management					1
CWR1-(51-SR)-S	STRAIGHT ROAD	Supply Chain Management	R	Straight road supply chain					1
CWR2-(52-CR)-D	CURVE ROAD	Design	R	Curve road design					1
CWR2-(52-CR)-I	CURVE ROAD	Site Installation	R	Curve road installation					1
CWR2-(52-CR)-M	CURVE ROAD	Project Management	A	Curve road management		1
			R	Curve road management					1
CWR2-(52-CR)-S	CURVE ROAD	Supply Chain Management	R	Curve road supply chain					1
CWR3-(6-BR01)-D	BRIDGE	Design	A	Bridge design		1
CWR3-(6-BR01)-I	BRIDGE	Site Installation	A	Bridge installation		1
CWR3-(6-BR01)-M	BRIDGE	Project Management	A	Bridge management		1
CWR3-(6-BR01)-S	BRIDGE	Supply Chain Management	A	Bridge supply chain		1
DAI-(@2-#)-D	ASSEMBLY INSTRUCTIONS	Design	A	Writing the assembly instructions					1
DUM-(@1-#)-D	USER MANUAL	Design	A	Writing the user manual					1
EME-(@-@)-D	All products	Design	A	E&M engineering					1
			I	E&M engineering					1
EME-(@-@)-M	All products	Project Management	A	E&M project management					1
			I	E&M project management					1
ENG-(@-@)-C	All products	Commissioning	A	Project commissioning					1
			C	Project commissioning					1
ENG-(@-@)-D	All products	Design	A	EM Engineering in charge of the consortium project engineering					1
			C	CW Engineering deputy consortium project engineering					1
HSC-(21-PS)-C	HANDHELD SPEED CONTROLLER	Commissioning	A	Handheld speed controller commissioning					1
HSC-(21-PS)-P	HANDHELD SPEED CONTROLLER	Production	A	Handheld speed controller production					1
HSC-(21-PS)-T	HANDHELD SPEED CONTROLLER	Testing	A	Handheld speed controller testing					1
MGM-(@-@)-M	All products	Project Management	A	CW project management in charge of the consortium PM				1
			R	EM Deputy consortium PM					1
MR-(@-#)-M	All products	Project Management	R	Writing monthly reports					1
PS-(2-PS)-D	POWER SUPPLY	Design	A	Power supply design					1
PS-(2-PS)-M	POWER SUPPLY	Project Management	A	Power supply management					1
PS-(2-PS)-S	POWER SUPPLY	Supply Chain Management	A	Power supply supply chain					1
PS-(22-PS)-C	POWER SUPPLY PACK	Commissioning	A	PS pack commissioning					1
PS-(22-PS)-P	POWER SUPPLY PACK	Production	A	PS pack production					1
PS-(22-PS)-T	POWER SUPPLY PACK	Testing	A	PS pack testing					1
PS-(23-PS)-P	POWER SUPPLY CABLES	Production	A	PS cables production					1
PS-(23-PS)-T	POWER SUPPLY CABLES	Testing	A	PS cables testing					1
PS-(3-@)-C	TRACK INFRASTRUCTURE	Commissioning	R	Track commissioning					1
PS-(3-@)-D	TRACK INFRASTRUCTURE	Design	R	Track design					1
PS-(3-@)-I	TRACK INFRASTRUCTURE	Site Installation	R	Track installation					1
PS-(3-@)-M	TRACK INFRASTRUCTURE	Project Management	A	Track management					1
			R	Track management					1
PS-(3-@)-S	TRACK INFRASTRUCTURE	Supply Chain Management	R	Track supply chain					1
PS-(3-@)-T	TRACK INFRASTRUCTURE	Testing	R	Track testing					1
SPCR-(532-CR)-P	CURVE ROAD SPARES	Production	A	Delivery of curve road spare parts		1
SPMO-(151-#)-S	MOTOR SPARES	Supply Chain Management	A	Delivery of motor spare parts			1
SPSC-(241-PS)-P	HANDHELD SPEED CONTROLLER SPARES	Production	A	Delivery of handheld speed controller spare parts					1
SPSR-(531-SR)-P	STRAIGHT ROAD SPARES	Production	A	Delivery of straight road spare parts		1

## PBS view
PBS view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

CWBS Name	- tout -
ABS Name	- tout -

Compter - PBS code				OBS Name
PBS Name	PBS Attribute	WBS code	GBS Name	Bridge sub-group	Building sub-group	Car sub-group	Civil Engineering	Civil Works JV	CW Project management	E&M JV	EM Engineering	EM Project management	Power supply sub-group	Road sub-group	Track sub-group
All products	0	CW-(@-@)-D	Project (All localisation)				1				1
		CW-(@-@)-M	Project (All localisation)					1			1
		EME-(@-@)-D	Project (All localisation)				1				1
		EME-(@-@)-M	Project (All localisation)					1			1
		ENG-(@-@)-C	Project (All localisation)				1				1
		ENG-(@-@)-D	Project (All localisation)				1				1
		MGM-(@-@)-M	Project (All localisation)					1		1
		MR-(@-#)-M	Project (No localisation)					1
ASSEMBLY INSTRUCTIONS	#	DAI-(@2-#)-D	Project (No localisation)				1
BRIDGE	1 bridge	CWR3-(6-BR01)-D	LONG BRIDGE	1
		CWR3-(6-BR01)-I	LONG BRIDGE	1
		CWR3-(6-BR01)-M	LONG BRIDGE	1
		CWR3-(6-BR01)-S	LONG BRIDGE	1
CARS	2 cars	CAR-(1-#)-C	Project (No localisation)			1
		CAR-(1-#)-D	Project (No localisation)			1
		CAR-(1-#)-M	Project (No localisation)			1
		CAR-(1-#)-P	Project (No localisation)			1
		CAR-(1-#)-S	Project (No localisation)			1
		CAR-(1-#)-T	Project (No localisation)			1
CURVE ROAD	All identical	CWR2-(52-CR)-D	All CURVE ROAD SECTIONS					1
		CWR2-(52-CR)-I	All CURVE ROAD SECTIONS					1
		CWR2-(52-CR)-M	All CURVE ROAD SECTIONS	1					1
		CWR2-(52-CR)-S	All CURVE ROAD SECTIONS					1
CURVE ROAD SPARES	1 curve road	SPCR-(532-CR)-P	All CURVE ROAD SECTIONS	1
GRANDSTAND BUILDING	2 buildings	CWB-(41-GB)-D	All GRANDSTAND BUILDING SECTIONS		1
		CWB-(41-GB)-I	All GRANDSTAND BUILDING SECTIONS		1
		CWB-(41-GB)-M	All GRANDSTAND BUILDING SECTIONS		1
		CWB-(41-GB)-S	All GRANDSTAND BUILDING SECTIONS		1
HANDHELD SPEED CONTROLLER	2 controllers	HSC-(21-PS)-C	POWER SUPPLY PACK CONNEXION					1
		HSC-(21-PS)-P	POWER SUPPLY PACK CONNEXION					1
		HSC-(21-PS)-T	POWER SUPPLY PACK CONNEXION					1
HANDHELD SPEED CONTROLLER SPARES	1 controller	SPSC-(241-PS)-P	POWER SUPPLY PACK CONNEXION					1
MOTOR SPARES	1 motor for car	SPMO-(151-#)-S	Project (No localisation)			1
POWER SUPPLY	0	PS-(2-PS)-D	POWER SUPPLY PACK CONNEXION					1
		PS-(2-PS)-M	POWER SUPPLY PACK CONNEXION					1
		PS-(2-PS)-S	POWER SUPPLY PACK CONNEXION					1
POWER SUPPLY CABLES	#	PS-(23-PS)-P	POWER SUPPLY PACK CONNEXION					1
		PS-(23-PS)-T	POWER SUPPLY PACK CONNEXION					1
POWER SUPPLY PACK	1 power supply pack	PS-(22-PS)-C	POWER SUPPLY PACK CONNEXION					1
		PS-(22-PS)-P	POWER SUPPLY PACK CONNEXION					1
		PS-(22-PS)-T	POWER SUPPLY PACK CONNEXION					1
STRAIGHT ROAD	All identical	CWR1-(51-SR)-D	All STRAIGHT ROAD SECTIONS					1
		CWR1-(51-SR)-I	All STRAIGHT ROAD SECTIONS					1
		CWR1-(51-SR)-M	All STRAIGHT ROAD SECTIONS	1					1
		CWR1-(51-SR)-S	All STRAIGHT ROAD SECTIONS					1
STRAIGHT ROAD SPARES	1 straight road	SPSR-(531-SR)-P	All STRAIGHT ROAD SECTIONS	1
TRACK INFRASTRUCTURE	0	PS-(3-@)-C	Project (All localisation)					1
		PS-(3-@)-D	Project (All localisation)					1
		PS-(3-@)-I	Project (All localisation)					1
		PS-(3-@)-M	Project (All localisation)					1		1
		PS-(3-@)-S	Project (All localisation)					1
		PS-(3-@)-T	Project (All localisation)					1
USER MANUAL	#	DUM-(@1-#)-D	Project (No localisation)					1

## GBS view
GBS view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

CWBS Name	- tout -
ABS Name	- tout -
WP Name	- tout -

Compter - PBS code			PBS code	PBS Name
			1	2	6	21	41	51	52	151	241	531	532	@	@1	@2
GBS code	GBS Attribute	GBS Name	CARS	POWER SUPPLY	BRIDGE	HANDHELD SPEED CONTROLLER	GRANDSTAND BUILDING	STRAIGHT ROAD	CURVE ROAD	MOTOR SPARES	HANDHELD SPEED CONTROLLER SPARES	STRAIGHT ROAD SPARES	CURVE ROAD SPARES	All products	USER MANUAL	ASSEMBLY INSTRUCTIONS
@	0	Project (All localisation)						12
#	0	Project (No localisation)	1					1				1	1	1
BR01	Position: 1.1 Length: 1.5 m	LONG BRIDGE			1
CR	0	All CURVE ROAD SECTIONS						1				1
GB	0	All GRANDSTAND BUILDING SECTIONS					1
PS	Position: 4.0	POWER SUPPLY PACK CONNEXION		1		1					1
SR	0	All STRAIGHT ROAD SECTIONS						1				1

## OBS view
OBS view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

CWBS Name	- tout -
PBS Name	- tout -
GBS Name	- tout -
ABS Name	- tout -

Compter - WBS code				ROLE code
OBS code	OBS Name	WP code	WBS code	R	A	C	I
BLG	Building sub-group	CW-BLD	CWB-(41-GB)-@		1
BRG	Bridge sub-group	CW-BRO	CWR3-(6-BR01)-@		1
			SPCR-(532-CR)-P		1
			SPSR-(531-SR)-P		1
CAG	Car sub-group	EM-CAR	CAR-(1-#)-@		1
			SPMO-(151-#)-P		1
CWG	Civil Works JV	CON-PM	MGM-(@-@)-@		1
EMG	E&M JV	CON-PM	MGM-(@-@)-@	1
ENC	Civil Engineering	CW-EN	CW-(@-@)-D		1
			DAI-(@2-#)-D		1
		EM-EN	EME-(@-@)-D				1
			ENG-(@-@)-D			1
ENE	EM Engineering	CW-EN	CW-(@-@)-D				1
		EM-EN	DUM-(@1-#)-D		1
			EME-(@-@)-D		1
			ENG-(@-@)-D		1
PMC	CW Project management	CW-PM	CW-(@-@)-M		1
		EM-PM	EME-(@-@)-M				1
PME	EM Project management	CON-PM	MR-(@-#)-M	1
		CW-PM	CW-(@-@)-M				1
		EM-PM	EME-(@-@)-M		1
PSG	Power supply sub-group	EM-PSTR	HSC-(21-PS)-@		1
			PS-(2-PS)-@		1
			SPSC-(241-PS)-P		1
ROAD	Road sub-group	CW-BRO	CWR1-(51-SR)-@	1
			CWR2-(52-CR)-@	1

## Time schedule
Time schedule		 progress	Calendar					© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
			Month 1					Month 2					Month 3
TBS code	TBS name		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	+ 1 year
MS	Contract master schedule
MS01	Contract signature
MS02	Monthly report
MS03	Delivery
MS04	Commissioning
MS05	Acceptance
MS06	Warranty period
PMS	Project master schedule
PMS-M	Milestones
PMS-M01	Project charter issue	100,0 %
PMS-M02	Assignment of the core team	0,0 %
PMS-M03	Consortium launch meeting	0,0 %
PMS-M04	Project consortium management plan first issue	0,0 %
PMS-M05	Development management plan first issue	0,0 %
PMS-M06	Interface management plan first issue	0,0 %
PMS-M07	Production/installation management plan first issue	0,0 %
PMS-M08	Testing/commissioning management plan first issue	0,0 %
PMS-M09	Progress meeting	0,0 %
PMS-M10	Design frozen	0,0 %
PMS-M11	Sourcing completed	0,0 %
PMS-M12	End of building installation	0,0 %
PMS-M13	End of roads installation	0,0 %
PMS-M14	End of track installation	0,0 %
PMS-M15	Delivery of all cars	0,0 %					1					2
PMS-M16	Delivery of all PS equipments	0,0 %
PMS-M17	End of integration test	0,0 %
PMS-M18	End of pre-commissioning	0,0 %
PMS-M19	End of commissioning	0,0 %
PMS-M20	Client acceptance date	0,0 %
PMS-M21	Invoices	0,0 %					50%					50%
PMS-P	Phases
PMS-P01	Launch	0,0 %
PMS-P02	Design	0,0 %
PMS-P03	Sourcing	0,0 %
PMS-P04	Production/installation	0,0 %
PMS-P05	Testing	0,0 %
PMS-P06	Pre-commissioning	0,0 %
PMS-P07	Commissioning	0,0 %
PMS-P08	Acceptance	0,0 %
PMS-P09	Warranty	0,0 %
MS-CW	CW group master schedule
MS-CW-M	CW Milestones
MS-CW-M01	Project CW group management plan first issue	0,0 %
MS-CW-M02	CW latest installation	0,0 %
MS-CW-WBS	CW WBS schedule
CW-(@-@)-M	CW project management	0,0 %
CW-(@-@)-D	CW engineering	0,0 %
CWB-(41-GB)-M	Building management	0,0 %
CWB-(41-GB)-D	Building design	0,0 %
CWB-(41-GB)-S	Building supply chain	0,0 %
CWB-(41-GB)-I	Building installation	0,0 %
CWR1-(51-SR)-M	Straight road management	0,0 %
CWR1-(51-SR)-D	Straight road design	0,0 %
CWR1-(51-SR)-S	Straight road supply chain	0,0 %
CWR1-(51-SR)-I	Straight road installation	0,0 %
CWR2-(52-CR)-M	Curve road management	0,0 %
CWR2-(52-CR)-D	Curve road design	0,0 %
CWR2-(52-CR)-S	Curve road supply chain	0,0 %
CWR2-(52-CR)-I	Curve road installation	0,0 %
CWR3-(6-BR01)-M	Bridge management	0,0 %
CWR3-(6-BR01)-D	Bridge design	0,0 %
CWR3-(6-BR01)-S	Bridge supply chain	0,0 %
CWR3-(6-BR01)-I	Bridge installation	0,0 %
DAI-(@2-#)-D	Writing the assembly instructions	0,0 %
SPCR-(532-CR)-P	Delivery of curve road spare parts	0,0 %
SPSR-(531-SR)-P	Delivery of straight road spare parts	0,0 %
MS-EM	EM group master schedule
MS-EM-M	EM Milestones
MS-EM-M01	Project EM group management plan first issue	0,0 %
MS-EM-M02	EM latest production	0,0 %
MS-EM-WBS	EM WBS schedule
EME-(@-@)-M	E&M project management	0,0 %
EME-(@-@)-D	E&M engineering	0,0 %
CAR-(1-#)-M	Car management	0,0 %
CAR-(1-#)-D	Car design	0,0 %
CAR-(1-#)-S	Car supply chain	0,0 %
CAR-(1-#)-P	Car production	0,0 %
CAR-(1-#)-T	Car testing	0,0 %
CAR-(1-#)-C	Car commissioning	0,0 %
PS-(2-PS)-M	Power supply management	0,0 %
PS-(2-PS)-D	Power supply design	0,0 %
PS-(2-PS)-S	Power supply supply chain	0,0 %
HSC-(21-PS)-P	Handheld speed controller production	0,0 %
HSC-(21-PS)-T	Handheld speed controller testing	0,0 %
HSC-(21-PS)-C	Handheld speed controller commissioning	0,0 %
PS-(22-PS)-P	PS pack production	0,0 %
PS-(22-PS)-T	PS pack testing	0,0 %
PS-(22-PS)-C	PS pack commissioning	0,0 %
PS-(23-PS)-P	PS cables production	0,0 %
PS-(23-PS)-T	PS cables testing	0,0 %
PS-(3-@)-M	Track management	0,0 %
PS-(3-@)-D	Track design	0,0 %
PS-(3-@)-S	Track supply chain	0,0 %
PS-(3-@)-I	Track installation	0,0 %
PS-(3-@)-T	Track testing	0,0 %
PS-(3-@)-C	Track commissioning	0,0 %
ENG-(@-@)-C	Project commissioning	0,0 %
DUM-(@1-#)-D	Writing the user manual	0,0 %
SPSC-(241-PS)-P	Delivery of handheld speed controller spare parts	0,0 %
SPMO-(151-#)-S	Delivery of motor spare parts	0,0 %

## Time–distance diagram
Position	PHASES / & / GBS		Calendar					Geo-temporal representation					© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
			Month 1					Month 2					Month 3
			1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	+ 1 year
	PHASES
	Launch
	Design
	Sourcing
	Production/installation
	Testing
	Pre-commissioning
	Commissioning
	Acceptance
	Warranty
	GBS
6	CR05	TEST ROAD					ROAD					TRACK					TEST ON TEST ROAD WITH 1 CAR					PRE-COMMISSIONING WITH 2 CARS					COMMISSIONING WITH THE CLIENT				ACCEPTANCE			WARRANTY
5,9
5,8
5,7
5,6
5,5
5,4	CR04					ROAD					TRACK
5,3
5,2
5,1
5
4,9
4,8	SR03					ROAD			ROAD				TRACK
4,7
4,6
4,5
4,4
4,3	CR03					ROAD					TRACK
4,2
4,1
4		PS					PS
3,9		CARS					1					2
3,8		CONTROLLERS					1					2
3,7	SR02	GB02					GB02					GB02					ROAD					TRACK
3,6
3,5
3,4
3,3
3,2	CR02					ROAD			TRACK
3,1
3
2,9
2,8
2,7
2,6	BR01					BRIDGE					BRIDGE					BRIDGE					TRACK
2,5
2,4
2,3
2,2
2,1
2					TRACK
1,9
1,8
1,7
1,6
1,5
1,4					TRACK
1,3
1,2
1,1	CR01					ROAD					TRACK
1
0,9
0,8
0,7
0,6
0,5	SR01	GB01					GB01					GB01					ROAD			TRACK
0,4
0,3
0,2
0,1

## TBSxWP view
TBSxWP view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Matrix dimensions	TBS x WP
Matrix type	MATRIX					 WBS progress at date	Expected WP physical progress			Expected WP cost progress
							End of month 1	End of month 2	End of month 3	End of month 1	End of month 2	End of month 3
Dimension 1	Code 1	Code 1 name	Matrix attribute	Code 2	Compter - Matrix attribute
TBS	CAR-(1-#)-C	Car commissioning	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CAR-(1-#)-D	Car design	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CAR-(1-#)-M	Car management	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CAR-(1-#)-P	Car production	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CAR-(1-#)-S	Car supply chain	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CAR-(1-#)-T	Car testing	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	CW-(@-@)-D	CW engineering	CW level	CW-EN	1	0 %	66 %	95 %	100 %
	CW-(@-@)-M	CW project management	CW level	CW-PM	1	0 %	33 %	66 %	100 %
	CWB-(41-GB)-D	Building design	CW level	CW-BLD	1	0 %	10 %	75 %	100 %	5 %	100 %	100 %
	CWB-(41-GB)-I	Building installation	CW level	CW-BLD	1	0 %	10 %	75 %	100 %	5 %	100 %	100 %
	CWB-(41-GB)-M	Building management	CW level	CW-BLD	1	0 %	10 %	75 %	100 %	5 %	100 %	100 %
	CWB-(41-GB)-S	Building supply chain	CW level	CW-BLD	1	0 %	10 %	75 %	100 %	5 %	100 %	100 %
	CWR1-(51-SR)-D	Straight road design	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR1-(51-SR)-I	Straight road installation	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR1-(51-SR)-M	Straight road management	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR1-(51-SR)-S	Straight road supply chain	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR2-(52-CR)-D	Curve road design	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR2-(52-CR)-I	Curve road installation	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR2-(52-CR)-M	Curve road management	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR2-(52-CR)-S	Curve road supply chain	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR3-(6-BR01)-D	Bridge design	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR3-(6-BR01)-I	Bridge installation	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR3-(6-BR01)-M	Bridge management	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	CWR3-(6-BR01)-S	Bridge supply chain	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	DAI-(@2-#)-D	Writing the assembly instructions	CW level	CW-EN	1	0 %	66 %	95 %	100 %
	DUM-(@1-#)-D	Writing the user manual	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	EME-(@-@)-D	E&M engineering	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	EME-(@-@)-M	E&M project management	EM level	EM-PM	1	0 %	33 %	77 %	100 %
	ENG-(@-@)-C	Project commissioning	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	HSC-(21-PS)-C	Handheld speed controller commissioning	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	HSC-(21-PS)-P	Handheld speed controller production	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	HSC-(21-PS)-T	Handheld speed controller testing	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	MS	Contract master schedule	Consortium level	CON-PM	1
	MS-CW	CW group master schedule	CW level	CW-PM	1
	MS-CW-M	CW Milestones	CW level	CW-PM	1
	MS-CW-M01	Project CW group management plan first issue	CW level	CW-PM	1	0 %	33 %	66 %	100 %
	MS-CW-M02	CW latest installation	CW level	CW-PM	1	0 %	33 %	66 %	100 %
	MS-CW-WBS	CW WBS schedule	CW level	CW-PM	1
	MS-EM	EM group master schedule	EM level	EM-PM	1
	MS-EM-M	EM Milestones	EM level	EM-PM	1
	MS-EM-M01	Project EM group management plan first issue	EM level	EM-PM	1	0 %	33 %	77 %	100 %
	MS-EM-M02	EM latest production	EM level	EM-PM	1	0 %	33 %	77 %	100 %
	MS-EM-WBS	EM WBS schedule	EM level	EM-PM	1
	MS01	Contract signature	Consortium level	CON-PM	1
	MS02	Monthly report	Consortium level	CON-PM	1
	MS03	Delivery	Consortium level	CON-PM	1
	MS04	Commissioning	EM level	EM-EN	1
	MS05	Acceptance	EM level	EM-EN	1
	MS06	Warranty period	Consortium level	CON-PM	1
	PMS	Project master schedule	Consortium level	CON-PM	1
	PMS-M	Milestones	Consortium level	CON-PM	1
	PMS-M01	Project charter issue	Consortium level	CON-PM	1	100 %	33 %	66 %	100 %
	PMS-M02	Assignment of the core team	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M03	Consortium launch meeting	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M04	Project consortium management plan first issue	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M05	Development management plan first issue	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-M06	Interface management plan first issue	CW level	CW-EN	1	0 %	66 %	95 %	100 %
	PMS-M07	Production/installation management plan first issue	CW level	CW-EN	1	0 %	66 %	95 %	100 %
	PMS-M08	Testing/commissioning management plan first issue	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-M09	Progress meeting	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M10	Design frozen	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M11	Sourcing completed	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M12	End of building installation	CW level	CW-BLD	1	0 %	10 %	75 %	100 %	5 %	100 %	100 %
	PMS-M13	End of roads installation	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PMS-M14	End of track installation	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PMS-M15	Delivery of all cars	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	PMS-M16	Delivery of all PS equipments	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PMS-M17	End of integration test	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-M18	End of pre-commissioning	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-M19	End of commissioning	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-M20	Client acceptance date	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-M21	Invoices	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P	Phases	Consortium level	CON-PM	1
	PMS-P01	Launch	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P02	Design	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P03	Sourcing	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P04	Production/installation	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P05	Testing	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P06	Pre-commissioning	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-P07	Commissioning	EM level	EM-EN	1	0 %	33 %	66 %	100 %
	PMS-P08	Acceptance	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PMS-P09	Warranty	Consortium level	CON-PM	1	0 %	33 %	66 %	100 %
	PS-(2-PS)-D	Power supply design	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(2-PS)-M	Power supply management	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(2-PS)-S	Power supply supply chain	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(22-PS)-C	PS pack commissioning	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(22-PS)-P	PS pack production	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(22-PS)-T	PS pack testing	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(23-PS)-P	PS cables production	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(23-PS)-T	PS cables testing	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-C	Track commissioning	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-D	Track design	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-I	Track installation	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-M	Track management	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-S	Track supply chain	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	PS-(3-@)-T	Track testing	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	SPCR-(532-CR)-P	Delivery of curve road spare parts	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	SPMO-(151-#)-S	Delivery of motor spare parts	EM level	EM-CAR	1	0 %	10 %	50 %	100 %	5 %	80 %	100 %
	SPSC-(241-PS)-P	Delivery of handheld speed controller spare parts	EM level	EM-PSTR	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %
	SPSR-(531-SR)-P	Delivery of straight road spare parts	CW level	CW-BRO	1	0 %	10 %	85 %	100 %	5 %	90 %	100 %

## SWOT
SWOT	Strengh, Weakness, Opporrtunity and Threat analysis		© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Organisational capabilities					Risk and opportunity management

Étiquettes de lignes		Somme - CAP attribute measures			Étiquettes de lignes		(vide)
Strength	1 Willingness to work for free.				Opportunity	1 Once the project has been delivered, another identical order may arrive, this time with a profit.
	Promoting individuals (e.g., video presentation on social media of each project member).					To increase the chances of success, make a video about the progress of the project to promote it. Then post it on social media.
	2 Every member of the team is passionate about their field of work.					2 Sponsoring the project
	Promote the presentation of each individual piece of work within the project team.					Prospect automotive and other companies to try to obtain subsidies by adding advertisements to the project.
	3 Other strength to define					3 Other opportunity to be define
	Enhancement measures to define					Improvement measures to be define
Weakness	1 The members of the project team did not know each other.				Risk / Threat	1 Xavier's 3D printer is unavailable or out of order.
	Organise a team-building session (for example, after work).					Have a plan B ready, for example with a Fab Lab at an engineering school.
	2 There are two juniors in the team.					2 Vincent's laser cutter is unavailable or out of order.
	Create a pairing between a junior and a senior member of the team.					Have a plan B ready, for example with a Fab Lab at an engineering school.
	3 There are no women on the team. We are losing creativity and open-mindedness.					3 Other risk to be define
	Promote the project to attract female members (for example, if there are no female candidates in engineering, perhaps a female candidate in communications?).					Mitigation measures to be define
	4 Other weakness to define
	Attenuating measures to define

## RESOURCE view
RESOURCE view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Matrix dimensions	WP x RBS
Matrix type	MATRIX

Compter - Matrix attribute						Dimension 2	Code 2
						RBS
Dimension 1	Code 1	Code 1 name	Code 1 attribute	Code 2 name	Matrix attribute	Alain	Christian	CW tools	EM tools	Jacques	Jean	Jules	Paul	Thomas	Vincent	WP budget (€)	Xavier	Yves
WP	CON-PM	CON Project management (only workload = free)	CON	H	Consortium deputy		1
					Consortium leader					1
	CW-BLD	CW buildings	BLG	H	WP leader					1
	CW-BRO	CW Road and bridge	BRG	H	WP leader					1
					WP member					1
	CW-EN	CW Engineering (only workload)	ENC	H	WP leader					1
				M	CW equipments			1
	CW-PM	CW Project management (only workload = free)	CWG	B	285					1
				H	CW leader					1
	CW-WAR	CW warranty provisions	CWG	B	15					1
				H	WP leader					1
	EM-CAR	EM Cars	CAG	H	WP leader	1
	EM-EN	EM Engineering (only workload = free)	ENE	H	WP leader					1
				M	EM equipments				1
	EM-PM	EM Project management (only workload = free)	EMG	B	190					1
				H	EM leader		1
	EM-PSTR	EM Power supply and tracks	PSG	H	WP leader					1
					WP member					1
	EM-WAR	EM warranty provisions	EMG	B	10					1
				H	WP leader		1

## PRODUCT INTERFACE view
PRODUCT INTERFACE view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Matrix dimensions	- multiple -
Matrix type	INTERFACE

Compter - Matrix attribute					Dimension 2	Code 2	Code 2 name
					PBS
					5	22	31	52
Dimension 1	Code 1	Code 1 name	Code 1 attribute	Matrix attribute	ROAD	POWER SUPPLY PACK	ELECTRICAL STRIPS	CURVE ROAD
PBS	12	CAR GUIDANCE SYSTEM	#	Electrical guidance for cars			1
				Mechanical guidance for cars			1
	14	PNEUMATICS	#	Mechanical adherence	1
	21	HANDHELD SPEED CONTROLLER	2 controllers	Contact point		1
	22	POWER SUPPLY PACK	1 power supply pack	Contact point on CR03				1
	31	ELECTRICAL STRIPS	2*6 meters (including bridge)	2 strips per road section	1

## FUNCTION view
FUNCTION view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Matrix dimensions	PBS x FBS
Matrix type	- tout -

Compter - Matrix attribute				Dimension 2	Code 2	Code 2 name
				FBS
				AC/DC	Adherence	Distribution on roads	Energy	Guidance	Mobility	Motorisation	Power capture	Speed control
Dimension 1	Code 1	Code 1 name	Matrix attribute	Rectifier	Stability through adhesion	Energy distribution	Energy function	Direction control	Mobility function	Mobility on roads	Transformer	Energy control
PBS	1	CARS	Movement					1
	2	POWER SUPPLY	Energy imput				1
	11	MOTOR	Movement transmission					1
	14	PNEUMATICS	Adherence on road		1
	21	HANDHELD SPEED CONTROLLER	Speed determination					1
	22	POWER SUPPLY PACK	Energy adaptation	1
			Energy captation					1
	31	ELECTRICAL STRIPS	Distribution			1
			Guidance					1

## MATRIX view
MATRIX view			© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

Matrix dimensions	PBS x FBS
Matrix type	- tout -

Compter - Matrix attribute				Dimension 2	Code 2	Code 2 name
				FBS
				AC/DC	Adherence	Distribution on roads	Energy	Guidance	Mobility	Motorisation	Power capture	Speed control
Dimension 1	Code 1	Code 1 name	Matrix attribute	Rectifier	Stability through adhesion	Energy distribution	Energy function	Direction control	Mobility function	Mobility on roads	Transformer	Energy control
PBS	1	CARS	Movement					1
	2	POWER SUPPLY	Energy imput				1
	11	MOTOR	Movement transmission					1
	14	PNEUMATICS	Adherence on road		1
	21	HANDHELD SPEED CONTROLLER	Speed determination					1
	22	POWER SUPPLY PACK	Energy adaptation	1
			Energy captation					1
	31	ELECTRICAL STRIPS	Distribution			1
			Guidance					1

## Input WBS tool
Allocated WBS code	WBS code	Issue date	CWBS code	PBS code	GBS code	ABS code	WP code	OBS code	ROLE code	WBS attribute	Level CWBS	Level PBS	Level GBS	Level ABS	Level OBS	CWBS Name	PBS Name	GBS Name	ABS Name	WP Name	OBS Name	CWBS Attribute	PBS Attribute	GBS Attribute	ABS Attribute	WP Attribute	OBS Attribute
PS-(3-@)-@-PSG-A	PS-(3-@)-@	12/10/25	PS	3	@	@	EM-PSTR	PSG	A	Track management	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Project (All activities)	EM Power supply and tracks	Power supply sub-group	1 power pack	0	0	All types of activities (M+D+S+P+T+I+C+L+W)	PSG	Sole proprietorship
Base	Zone Valeurs	Zone Formules
WBSDataBase	C2:K2	A2:B2 & L2:Z2	Fin de zone de structure de données
	Creation of an allocated WBS element						© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
	Create the WBS element			WBS element selected :
	CWBS code :	PS	Power supply	PS-(3-@)-@
	PBS code :	3	TRACK INFRASTRUCTURE	Associated WP : EM Power supply and tracks
	GBS code :	@	Project (All localisation)	Press the button to validate this new WBS element..
	ABS code :	@	Project (All activities)
	WP code :	EM-PSTR	EM Power supply and tracks
	Responsibility associated to this WBS element :			WBS element allocated as :
	OBS code :	PSG	Power supply sub-group	PSG-A
	ROLE code :	A	Accountable	Work package organisation owner:
	WBS attribute :	Track management		PSG
Add this new WBS item

## WBSDataBase
Allocated WBS code	WBS code	Issue date	CWBS code	PBS code	GBS code	ABS code	WP code	OBS code	ROLE code	WBS remark	Level CWBS	Level PBS	Level GBS	Level ABS	Level OBS	CWBS Name	PBS Name	GBS Name	ABS Name	WP Name	OBS Name	CWBS Attribute	PBS Attribute	GBS Attribute	ABS Attribute	WP Attribute	OBS Attribute	© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

MR-(@-#)-M-PME-R	MR-(@-#)-M	03/10/25	MR	@	#	M	CON-PM	PME	R	Writing monthly reports	2	1	1	1	3	Monthly report	All products	Project (No localisation)	Project Management	CON Project management (only workload = free)	EM Project management	0	0	0	All Project Management type of activities	CON	Sole proprietorship
DAI-(@2-#)-D-ENC-A	DAI-(@2-#)-D	03/10/25	DAI	@2	#	D	CW-EN	ENC	A	Writing the assembly instructions	2	2	1	1	3	Assembly instruction	ASSEMBLY INSTRUCTIONS	Project (No localisation)	Design	CW Engineering (only workload)	Civil Engineering	1 copy	#	0	All Design type of activities	ENC	Sole proprietorship
DUM-(@1-#)-D-ENE-A	DUM-(@1-#)-D	03/10/25	DUM	@1	#	D	EM-EN	ENE	A	Writing the user manual	2	2	1	1	3	User manual	USER MANUAL	Project (No localisation)	Design	EM Engineering (only workload = free)	EM Engineering	1 copy	#	0	All Design type of activities	ENE	Sole proprietorship

SPCR-(532-CR)-P-BRG-A	SPCR-(532-CR)-P	03/10/25	SPCR	532	CR	P	CW-BRO	BRG	A	Delivery of curve road spare parts	2	3	1	1	3	Curve road	CURVE ROAD SPARES	All CURVE ROAD SECTIONS	Production	CW Road and bridge	Bridge sub-group	1 curve road element	1 curve road	0	All Production type of activities	BRG	Sole proprietorship
SPSR-(531-SR)-P-BRG-A	SPSR-(531-SR)-P	03/10/25	SPSR	531	SR	P	CW-BRO	BRG	A	Delivery of straight road spare parts	2	3	1	1	3	Straight road	STRAIGHT ROAD SPARES	All STRAIGHT ROAD SECTIONS	Production	CW Road and bridge	Bridge sub-group	1 straight road element	1 straight road	0	All Production type of activities	BRG	Sole proprietorship
SPSC-(241-PS)-P-PSG-A	SPSC-(241-PS)-P	03/10/25	SPSC	241	PS	P	EM-PSTR	PSG	A	Delivery of handheld speed controller spare parts	2	3	1	1	3	Handheld speed controller	HANDHELD SPEED CONTROLLER SPARES	POWER SUPPLY PACK CONNEXION	Production	EM Power supply and tracks	Power supply sub-group	1 controller	1 controller	Position: 4.0	All Production type of activities	PSG	Sole proprietorship
SPMO-(151-#)-S-CAG-A	SPMO-(151-#)-S	03/10/25	SPMO	151	#	S	EM-CAR	CAG	A	Delivery of motor spare parts	2	3	1	1	3	Motor	MOTOR SPARES	Project (No localisation)	Supply Chain Management	EM Cars	Car sub-group	1 motor for car	1 motor for car	0	All Supply Chain Management type of activities	CAG	Sole proprietorship

PS-(2-PS)-M-PSG-A	PS-(2-PS)-M	03/10/25	PS	2	PS	M	EM-PSTR	PSG	A	Power supply management	2	1	1	1	3	Power supply	POWER SUPPLY	POWER SUPPLY PACK CONNEXION	Project Management	EM Power supply and tracks	Power supply sub-group	1 power pack	0	Position: 4.0	All Project Management type of activities	PSG	Sole proprietorship
PS-(2-PS)-D-PSG-A	PS-(2-PS)-D	12/10/25	PS	2	PS	D	EM-PSTR	PSG	A	Power supply design	2	1	1	1	3	Power supply	POWER SUPPLY	POWER SUPPLY PACK CONNEXION	Design	EM Power supply and tracks	Power supply sub-group	1 power pack	0	Position: 4.0	All Design type of activities	PSG	Sole proprietorship
PS-(2-PS)-S-PSG-A	PS-(2-PS)-S	12/10/25	PS	2	PS	S	EM-PSTR	PSG	A	Power supply supply chain	2	1	1	1	3	Power supply	POWER SUPPLY	POWER SUPPLY PACK CONNEXION	Supply Chain Management	EM Power supply and tracks	Power supply sub-group	1 power pack	0	Position: 4.0	All Supply Chain Management type of activities	PSG	Sole proprietorship
HSC-(21-PS)-P-PSG-A	HSC-(21-PS)-P	03/10/25	HSC	21	PS	P	EM-PSTR	PSG	A	Handheld speed controller production	2	2	1	1	3	Handheld speed controller	HANDHELD SPEED CONTROLLER	POWER SUPPLY PACK CONNEXION	Production	EM Power supply and tracks	Power supply sub-group	2 controllers	2 controllers	Position: 4.0	All Production type of activities	PSG	Sole proprietorship
HSC-(21-PS)-T-PSG-A	HSC-(21-PS)-T	03/10/25	HSC	21	PS	T	EM-PSTR	PSG	A	Handheld speed controller testing	2	2	1	1	3	Handheld speed controller	HANDHELD SPEED CONTROLLER	POWER SUPPLY PACK CONNEXION	Testing	EM Power supply and tracks	Power supply sub-group	2 controllers	2 controllers	Position: 4.0	All Testing type of activities	PSG	Sole proprietorship
HSC-(21-PS)-C-PSG-A	HSC-(21-PS)-C	03/10/25	HSC	21	PS	C	EM-PSTR	PSG	A	Handheld speed controller commissioning	2	2	1	1	3	Handheld speed controller	HANDHELD SPEED CONTROLLER	POWER SUPPLY PACK CONNEXION	Commissioning	EM Power supply and tracks	Power supply sub-group	2 controllers	2 controllers	Position: 4.0	All Commissioning type of activities	PSG	Sole proprietorship
PS-(22-PS)-P-PSG-A	PS-(22-PS)-P	12/10/25	PS	22	PS	P	EM-PSTR	PSG	A	PS pack production	2	2	1	1	3	Power supply	POWER SUPPLY PACK	POWER SUPPLY PACK CONNEXION	Production	EM Power supply and tracks	Power supply sub-group	1 power pack	1 power supply pack	Position: 4.0	All Production type of activities	PSG	Sole proprietorship
PS-(22-PS)-T-PSG-A	PS-(22-PS)-T	12/10/25	PS	22	PS	T	EM-PSTR	PSG	A	PS pack testing	2	2	1	1	3	Power supply	POWER SUPPLY PACK	POWER SUPPLY PACK CONNEXION	Testing	EM Power supply and tracks	Power supply sub-group	1 power pack	1 power supply pack	Position: 4.0	All Testing type of activities	PSG	Sole proprietorship
PS-(22-PS)-C-PSG-A	PS-(22-PS)-C	12/10/25	PS	22	PS	C	EM-PSTR	PSG	A	PS pack commissioning	2	2	1	1	3	Power supply	POWER SUPPLY PACK	POWER SUPPLY PACK CONNEXION	Commissioning	EM Power supply and tracks	Power supply sub-group	1 power pack	1 power supply pack	Position: 4.0	All Commissioning type of activities	PSG	Sole proprietorship
PS-(23-PS)-P-PSG-A	PS-(23-PS)-P	12/10/25	PS	23	PS	P	EM-PSTR	PSG	A	PS cables production	2	2	1	1	3	Power supply	POWER SUPPLY CABLES	POWER SUPPLY PACK CONNEXION	Production	EM Power supply and tracks	Power supply sub-group	1 power pack	#	Position: 4.0	All Production type of activities	PSG	Sole proprietorship
PS-(23-PS)-T-PSG-A	PS-(23-PS)-T	12/10/25	PS	23	PS	T	EM-PSTR	PSG	A	PS cables testing	2	2	1	1	3	Power supply	POWER SUPPLY CABLES	POWER SUPPLY PACK CONNEXION	Testing	EM Power supply and tracks	Power supply sub-group	1 power pack	#	Position: 4.0	All Testing type of activities	PSG	Sole proprietorship

PS-(3-@)-M-PSG-A	PS-(3-@)-M	12/10/25	PS	3	@	M	EM-PSTR	PSG	A	Track management	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Project Management	EM Power supply and tracks	Power supply sub-group	1 power pack	0	0	All Project Management type of activities	PSG	Sole proprietorship
PS-(3-@)-M-TRG-R	PS-(3-@)-M	12/10/25	PS	3	@	M	EM-PSTR	TRG	R	Track management	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Project Management	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Project Management type of activities	PSG	Sole proprietorship
PS-(3-@)-D-TRG-R	PS-(3-@)-D	12/10/25	PS	3	@	D	EM-PSTR	TRG	R	Track design	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Design	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Design type of activities	PSG	Sole proprietorship
PS-(3-@)-S-TRG-R	PS-(3-@)-S	12/10/25	PS	3	@	S	EM-PSTR	TRG	R	Track supply chain	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Supply Chain Management	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Supply Chain Management type of activities	PSG	Sole proprietorship
PS-(3-@)-I-TRG-R	PS-(3-@)-I	12/10/25	PS	3	@	I	EM-PSTR	TRG	R	Track installation	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Site Installation	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Site Installation type of activities	PSG	Sole proprietorship
PS-(3-@)-T-TRG-R	PS-(3-@)-T	12/10/25	PS	3	@	T	EM-PSTR	TRG	R	Track testing	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Testing	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Testing type of activities	PSG	Sole proprietorship
PS-(3-@)-C-TRG-R	PS-(3-@)-C	12/10/25	PS	3	@	C	EM-PSTR	TRG	R	Track commissioning	2	1	1	1	3	Power supply	TRACK INFRASTRUCTURE	Project (All localisation)	Commissioning	EM Power supply and tracks	Track sub-group	1 power pack	0	0	All Commissioning type of activities	PSG	Sole proprietorship

CAR-(1-#)-M-CAG-A	CAR-(1-#)-M	03/10/25	CAR	1	#	M	EM-CAR	CAG	A	Car management	2	1	1	1	3	Cars	CARS	Project (No localisation)	Project Management	EM Cars	Car sub-group	2 cars	2 cars	0	All Project Management type of activities	CAG	Sole proprietorship
CAR-(1-#)-D-CAG-A	CAR-(1-#)-D	12/10/25	CAR	1	#	D	EM-CAR	CAG	A	Car design	2	1	1	1	3	Cars	CARS	Project (No localisation)	Design	EM Cars	Car sub-group	2 cars	2 cars	0	All Design type of activities	CAG	Sole proprietorship
CAR-(1-#)-S-CAG-A	CAR-(1-#)-S	12/10/25	CAR	1	#	S	EM-CAR	CAG	A	Car supply chain	2	1	1	1	3	Cars	CARS	Project (No localisation)	Supply Chain Management	EM Cars	Car sub-group	2 cars	2 cars	0	All Supply Chain Management type of activities	CAG	Sole proprietorship
CAR-(1-#)-P-CAG-A	CAR-(1-#)-P	12/10/25	CAR	1	#	P	EM-CAR	CAG	A	Car production	2	1	1	1	3	Cars	CARS	Project (No localisation)	Production	EM Cars	Car sub-group	2 cars	2 cars	0	All Production type of activities	CAG	Sole proprietorship
CAR-(1-#)-T-CAG-A	CAR-(1-#)-T	12/10/25	CAR	1	#	T	EM-CAR	CAG	A	Car testing	2	1	1	1	3	Cars	CARS	Project (No localisation)	Testing	EM Cars	Car sub-group	2 cars	2 cars	0	All Testing type of activities	CAG	Sole proprietorship
CAR-(1-#)-C-CAG-A	CAR-(1-#)-C	12/10/25	CAR	1	#	C	EM-CAR	CAG	A	Car commissioning	2	1	1	1	3	Cars	CARS	Project (No localisation)	Commissioning	EM Cars	Car sub-group	2 cars	2 cars	0	All Commissioning type of activities	CAG	Sole proprietorship

CWB-(41-GB)-M-BLG-A	CWB-(41-GB)-M	03/10/25	CWB	41	GB	M	CW-BLD	BLG	A	Building management	2	2	1	1	3	Grandstand building	GRANDSTAND BUILDING	All GRANDSTAND BUILDING SECTIONS	Project Management	CW buildings	Building sub-group	2 buildings	2 buildings	0	All Project Management type of activities	BLG	Sole proprietorship
CWB-(41-GB)-D-BLG-A	CWB-(41-GB)-D	12/10/25	CWB	41	GB	D	CW-BLD	BLG	A	Building design	2	2	1	1	3	Grandstand building	GRANDSTAND BUILDING	All GRANDSTAND BUILDING SECTIONS	Design	CW buildings	Building sub-group	2 buildings	2 buildings	0	All Design type of activities	BLG	Sole proprietorship
CWB-(41-GB)-S-BLG-A	CWB-(41-GB)-S	12/10/25	CWB	41	GB	S	CW-BLD	BLG	A	Building supply chain	2	2	1	1	3	Grandstand building	GRANDSTAND BUILDING	All GRANDSTAND BUILDING SECTIONS	Supply Chain Management	CW buildings	Building sub-group	2 buildings	2 buildings	0	All Supply Chain Management type of activities	BLG	Sole proprietorship
CWB-(41-GB)-I-BLG-A	CWB-(41-GB)-I	12/10/25	CWB	41	GB	I	CW-BLD	BLG	A	Building installation	2	2	1	1	3	Grandstand building	GRANDSTAND BUILDING	All GRANDSTAND BUILDING SECTIONS	Site Installation	CW buildings	Building sub-group	2 buildings	2 buildings	0	All Site Installation type of activities	BLG	Sole proprietorship

CWR3-(6-BR01)-M-BRG-A	CWR3-(6-BR01)-M	03/10/25	CWR3	6	BR01	M	CW-BRO	BRG	A	Bridge management	3	1	1	1	3	Bridge	BRIDGE	LONG BRIDGE	Project Management	CW Road and bridge	Bridge sub-group	1 long bridge	1 bridge	Position: 1.1 Length: 1.5 m	All Project Management type of activities	BRG	Sole proprietorship
CWR3-(6-BR01)-D-BRG-A	CWR3-(6-BR01)-D	12/10/25	CWR3	6	BR01	D	CW-BRO	BRG	A	Bridge design	3	1	1	1	3	Bridge	BRIDGE	LONG BRIDGE	Design	CW Road and bridge	Bridge sub-group	1 long bridge	1 bridge	Position: 1.1 Length: 1.5 m	All Design type of activities	BRG	Sole proprietorship
CWR3-(6-BR01)-S-BRG-A	CWR3-(6-BR01)-S	12/10/25	CWR3	6	BR01	S	CW-BRO	BRG	A	Bridge supply chain	3	1	1	1	3	Bridge	BRIDGE	LONG BRIDGE	Supply Chain Management	CW Road and bridge	Bridge sub-group	1 long bridge	1 bridge	Position: 1.1 Length: 1.5 m	All Supply Chain Management type of activities	BRG	Sole proprietorship
CWR3-(6-BR01)-I-BRG-A	CWR3-(6-BR01)-I	12/10/25	CWR3	6	BR01	I	CW-BRO	BRG	A	Bridge installation	3	1	1	1	3	Bridge	BRIDGE	LONG BRIDGE	Site Installation	CW Road and bridge	Bridge sub-group	1 long bridge	1 bridge	Position: 1.1 Length: 1.5 m	All Site Installation type of activities	BRG	Sole proprietorship

CWR2-(52-CR)-M-BRG-A	CWR2-(52-CR)-M	03/10/25	CWR2	52	CR	M	CW-BRO	BRG	A	Curve road management	3	2	1	1	3	Curve road elements	CURVE ROAD	All CURVE ROAD SECTIONS	Project Management	CW Road and bridge	Bridge sub-group	All identical	All identical	0	All Project Management type of activities	BRG	Sole proprietorship
CWR2-(52-CR)-M-ROAD-R	CWR2-(52-CR)-M	03/10/25	CWR2	52	CR	M	CW-BRO	ROAD	R	Curve road management	3	2	1	1	3	Curve road elements	CURVE ROAD	All CURVE ROAD SECTIONS	Project Management	CW Road and bridge	Road sub-group	All identical	All identical	0	All Project Management type of activities	BRG	Sole proprietorship
CWR2-(52-CR)-D-ROAD-R	CWR2-(52-CR)-D	12/10/25	CWR2	52	CR	D	CW-BRO	ROAD	R	Curve road design	3	2	1	1	3	Curve road elements	CURVE ROAD	All CURVE ROAD SECTIONS	Design	CW Road and bridge	Road sub-group	All identical	All identical	0	All Design type of activities	BRG	Sole proprietorship
CWR2-(52-CR)-S-ROAD-R	CWR2-(52-CR)-S	12/10/25	CWR2	52	CR	S	CW-BRO	ROAD	R	Curve road supply chain	3	2	1	1	3	Curve road elements	CURVE ROAD	All CURVE ROAD SECTIONS	Supply Chain Management	CW Road and bridge	Road sub-group	All identical	All identical	0	All Supply Chain Management type of activities	BRG	Sole proprietorship
CWR2-(52-CR)-I-ROAD-R	CWR2-(52-CR)-I	12/10/25	CWR2	52	CR	I	CW-BRO	ROAD	R	Curve road installation	3	2	1	1	3	Curve road elements	CURVE ROAD	All CURVE ROAD SECTIONS	Site Installation	CW Road and bridge	Road sub-group	All identical	All identical	0	All Site Installation type of activities	BRG	Sole proprietorship

CWR1-(51-SR)-M-BRG-A	CWR1-(51-SR)-M	03/10/25	CWR1	51	SR	M	CW-BRO	BRG	A	Straight road management	3	2	1	1	3	Straight road elements	STRAIGHT ROAD	All STRAIGHT ROAD SECTIONS	Project Management	CW Road and bridge	Bridge sub-group	All identical	All identical	0	All Project Management type of activities	BRG	Sole proprietorship
CWR1-(51-SR)-M-ROAD-R	CWR1-(51-SR)-M	03/10/25	CWR1	51	SR	M	CW-BRO	ROAD	R	Straight road management	3	2	1	1	3	Straight road elements	STRAIGHT ROAD	All STRAIGHT ROAD SECTIONS	Project Management	CW Road and bridge	Road sub-group	All identical	All identical	0	All Project Management type of activities	BRG	Sole proprietorship
CWR1-(51-SR)-D-ROAD-R	CWR1-(51-SR)-D	12/10/25	CWR1	51	SR	D	CW-BRO	ROAD	R	Straight road design	3	2	1	1	3	Straight road elements	STRAIGHT ROAD	All STRAIGHT ROAD SECTIONS	Design	CW Road and bridge	Road sub-group	All identical	All identical	0	All Design type of activities	BRG	Sole proprietorship
CWR1-(51-SR)-S-ROAD-R	CWR1-(51-SR)-S	12/10/25	CWR1	51	SR	S	CW-BRO	ROAD	R	Straight road supply chain	3	2	1	1	3	Straight road elements	STRAIGHT ROAD	All STRAIGHT ROAD SECTIONS	Supply Chain Management	CW Road and bridge	Road sub-group	All identical	All identical	0	All Supply Chain Management type of activities	BRG	Sole proprietorship
CWR1-(51-SR)-I-ROAD-R	CWR1-(51-SR)-I	12/10/25	CWR1	51	SR	I	CW-BRO	ROAD	R	Straight road installation	3	2	1	1	3	Straight road elements	STRAIGHT ROAD	All STRAIGHT ROAD SECTIONS	Site Installation	CW Road and bridge	Road sub-group	All identical	All identical	0	All Site Installation type of activities	BRG	Sole proprietorship

CW-(@-@)-D-ENC-A	CW-(@-@)-D	03/10/25	CW	@	@	D	CW-EN	ENC	A	CW engineering	1	1	1	1	3	Civil works	All products	Project (All localisation)	Design	CW Engineering (only workload)	Civil Engineering	0	0	0	All Design type of activities	ENC	Sole proprietorship
CW-(@-@)-D-ENE-I	CW-(@-@)-D	03/10/25	CW	@	@	D	CW-EN	ENE	I	CW engineering	1	1	1	1	3	Civil works	All products	Project (All localisation)	Design	CW Engineering (only workload)	EM Engineering	0	0	0	All Design type of activities	ENC	Sole proprietorship
CW-(@-@)-M-PMC-A	CW-(@-@)-M	03/10/25	CW	@	@	M	CW-PM	PMC	A	CW project management	1	1	1	1	3	Civil works	All products	Project (All localisation)	Project Management	CW Project management (only workload = free)	CW Project management	0	0	0	All Project Management type of activities	CWG	Sole proprietorship
CW-(@-@)-M-PME-I	CW-(@-@)-M	03/10/25	CW	@	@	M	CW-PM	PME	I	CW project management	1	1	1	1	3	Civil works	All products	Project (All localisation)	Project Management	CW Project management (only workload = free)	EM Project management	0	0	0	All Project Management type of activities	CWG	Sole proprietorship

EME-(@-@)-D-ENC-I	EME-(@-@)-D	03/10/25	EME	@	@	D	EM-EN	ENC	I	E&M engineering	1	1	1	1	3	Electro-mechanical equipments	All products	Project (All localisation)	Design	EM Engineering (only workload = free)	Civil Engineering	0	0	0	All Design type of activities	ENE	Sole proprietorship
EME-(@-@)-D-ENE-A	EME-(@-@)-D	03/10/25	EME	@	@	D	EM-EN	ENE	A	E&M engineering	1	1	1	1	3	Electro-mechanical equipments	All products	Project (All localisation)	Design	EM Engineering (only workload = free)	EM Engineering	0	0	0	All Design type of activities	ENE	Sole proprietorship
EME-(@-@)-M-PMC-I	EME-(@-@)-M	03/10/25	EME	@	@	M	EM-PM	PMC	I	E&M project management	1	1	1	1	3	Electro-mechanical equipments	All products	Project (All localisation)	Project Management	EM Project management (only workload = free)	CW Project management	0	0	0	All Project Management type of activities	EMG	Sole proprietorship
EME-(@-@)-M-PME-A	EME-(@-@)-M	03/10/25	EME	@	@	M	EM-PM	PME	A	E&M project management	1	1	1	1	3	Electro-mechanical equipments	All products	Project (All localisation)	Project Management	EM Project management (only workload = free)	EM Project management	0	0	0	All Project Management type of activities	EMG	Sole proprietorship

ENG-(@-@)-D-ENE-A	ENG-(@-@)-D	03/10/25	ENG	@	@	D	EM-EN	ENE	A	EM Engineering in charge of the consortium project engineering	1	1	1	1	3	Engineering	All products	Project (All localisation)	Design	EM Engineering (only workload = free)	EM Engineering	0	0	0	All Design type of activities	ENE	Sole proprietorship
ENG-(@-@)-D-ENC-C	ENG-(@-@)-D	03/10/25	ENG	@	@	D	EM-EN	ENC	C	CW Engineering deputy consortium project engineering	1	1	1	1	3	Engineering	All products	Project (All localisation)	Design	EM Engineering (only workload = free)	Civil Engineering	0	0	0	All Design type of activities	ENE	Sole proprietorship
ENG-(@-@)-C-ENE-A	ENG-(@-@)-C	03/10/25	ENG	@	@	C	EM-EN	ENE	A	Project commissioning	1	1	1	1	3	Engineering	All products	Project (All localisation)	Commissioning	EM Engineering (only workload = free)	EM Engineering	0	0	0	All Commissioning type of activities	ENE	Sole proprietorship
ENG-(@-@)-C-ENC-C	ENG-(@-@)-C	03/10/25	ENG	@	@	C	EM-EN	ENC	C	Project commissioning	1	1	1	1	3	Engineering	All products	Project (All localisation)	Commissioning	EM Engineering (only workload = free)	Civil Engineering	0	0	0	All Commissioning type of activities	ENE	Sole proprietorship

MGM-(@-@)-M-CWG-A	MGM-(@-@)-M	03/10/25	MGM	@	@	M	CON-PM	CWG	A	CW project management in charge of the consortium PM	1	1	1	1	2	Project Management	All products	Project (All localisation)	Project Management	CON Project management (only workload = free)	Civil Works JV	0	0	0	All Project Management type of activities	CON	Integrated joint venture
MGM-(@-@)-M-EMG-R	MGM-(@-@)-M	03/10/25	MGM	@	@	M	CON-PM	EMG	R	EM Deputy consortium PM	1	1	1	1	2	Project Management	All products	Project (All localisation)	Project Management	CON Project management (only workload = free)	E&M JV	0	0	0	All Project Management type of activities	CON	Integrated joint venture

## Input INTERFACE tool
Matrix dimensions	Issue date	Dimension 1	Dimension 2	Matrix type	Code 1	Code 2	Matrix attribute	Level code 1	Level code 2	Code 1 name	Code 2 name	Code 1 attribute	Code 2 attribute
PBS x PBS	12/10/25	PBS	PBS	INTERFACE	31	5	#	2	1	ELECTRICAL STRIPS	ROAD	2*6 meters (including bridge)	ROAD
Base	Zone Valeurs	Zone Formules
MATRIXDataBase	B2:H2	A2:A2 & I2:Z2	Fin de zone de structure de données
Creation of an interface element					© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
	PBS x PBS
	Interface type :	PBS	Product breakdown structure
	PBS code 1 :	31	ELECTRICAL STRIPS
	PBS code 2 :	5	ROAD
	Attribute assignment :	#
Add this new inferface item

## Input MATRIX tool
Matrix dimensions	Issue date	Dimension 1	Dimension 2	Matrix type	Code 1	Code 2	Matrix attribute	Level code 1	Level code 2	Code 1 name	Code 2 name	Code 1 attribute	Code 2 attribute
PBS x FBS	12/10/25	PBS	FBS	MATRIX	1	Guidance	#	1	2	CARS	Direction control	2 cars	Direction control
Base	Zone Valeurs	Zone Formules
MATRIXDataBase	B2:H2	A2:A2 & I2:Z2	Fin de zone de structure de données
Assigning an FBS element to a PBS element.					© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0
	PBS x FBS
	Allocation for :	PBS	Product breakdown structure
	from :	FBS	Function breakdown structure
	PBS code	1	CARS
	FBS code	Guidance	Direction control
	Attribute assignment :	#
Add this new matrix item

## MATRIXDataBase
Matrix dimensions	Issue date	Dimension 1	Dimension 2	Matrix type	Code 1	Code 2	Matrix attribute	Level code 1	Level code 2	Code 1 name	Code 2 name	Code 1 attribute	Code 2 attribute	© 2025 Christian Jousselin / Contrat Creative Commons BY-NC-ND 4.0

PBS x PBS	06/10/25	PBS	PBS	INTERFACE	31	5	2 strips per road section	2	1	ELECTRICAL STRIPS	ROAD	2*6 meters (including bridge)	ROAD
PBS x PBS	06/10/25	PBS	PBS	INTERFACE	22	52	Contact point on CR03	2	2	POWER SUPPLY PACK	CURVE ROAD	1 power supply pack	CURVE ROAD
PBS x PBS	06/10/25	PBS	PBS	INTERFACE	21	22	Contact point	2	2	HANDHELD SPEED CONTROLLER	POWER SUPPLY PACK	2 controllers	POWER SUPPLY PACK
PBS x PBS	06/10/25	PBS	PBS	INTERFACE	14	5	Mechanical adherence	2	1	PNEUMATICS	ROAD	#	ROAD
PBS x PBS	06/10/25	PBS	PBS	INTERFACE	12	31	Electrical guidance for cars	2	2	CAR GUIDANCE SYSTEM	ELECTRICAL STRIPS	#	ELECTRICAL STRIPS
PBS x PBS	06/10/25	PBS	PBS	INTERFACE	12	31	Mechanical guidance for cars	2	2	CAR GUIDANCE SYSTEM	ELECTRICAL STRIPS	#	ELECTRICAL STRIPS

WP x RBS	06/10/25	WP	RBS	MATRIX	CW-WAR	WP budget (€)	15	0	0	CW warranty provisions	B	CWG	B
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-WAR	WP budget (€)	10	0	0	EM warranty provisions	B	EMG	B
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-WAR	Christian	WP leader	0	0601020305	EM warranty provisions	H	EMG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-PSTR	Yves	WP member	0	0601020314	EM Power supply and tracks	H	PSG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-PSTR	Xavier	WP leader	0	0601020313	EM Power supply and tracks	H	PSG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-CAR	Alain	WP leader	0	0601020304	EM Cars	H	CAG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-BRO	Thomas	WP member	0	0601020311	CW Road and bridge	H	BRG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-WAR	Jules	WP leader	0	0601020308	CW warranty provisions	H	CWG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-BLD	Paul	WP leader	0	0601020310	CW buildings	H	BLG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-BRO	Vincent	WP leader	0	0601020312	CW Road and bridge	H	BRG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-PM	WP budget (€)	285	0	0	CW Project management (only workload = free)	B	CWG	B
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-PM	WP budget (€)	190	0	0	EM Project management (only workload = free)	B	EMG	B
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-EN	EM tools	EM equipments	0	Xavier’ home	EM Engineering (only workload = free)	M	ENE	M
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-EN	CW tools	CW equipments	0	Vincent’ home	CW Engineering (only workload)	M	ENC	M
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-PM	Christian	EM leader	0	0601020305	EM Project management (only workload = free)	H	EMG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-EN	Jean	WP leader	0	0601020307	CW Engineering (only workload)	H	ENC	H
WP x RBS	06/10/25	WP	RBS	MATRIX	EM-EN	Jacques	WP leader	0	0601020306	EM Engineering (only workload = free)	H	ENE	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CW-PM	Jules	CW leader	0	0601020308	CW Project management (only workload = free)	H	CWG	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CON-PM	Jules	Consortium leader	0	0601020308	CON Project management (only workload = free)	H	CON	H
WP x RBS	06/10/25	WP	RBS	MATRIX	CON-PM	Christian	Consortium deputy	0	0601020305	CON Project management (only workload = free)	H	CON	H

PBS x FBS	06/10/25	PBS	FBS	MATRIX	2	Energy	Energy imput	1	1	POWER SUPPLY	Energy function	0	Energy function
PBS x FBS	06/10/25	PBS	FBS	MATRIX	22	AC/DC	Energy adaptation	2	2	POWER SUPPLY PACK	Rectifier	1 power supply pack	Rectifier
PBS x FBS	06/10/25	PBS	FBS	MATRIX	22	Power capture	Energy captation	2	2	POWER SUPPLY PACK	Transformer	1 power supply pack	Transformer
PBS x FBS	06/10/25	PBS	FBS	MATRIX	21	Speed control	Speed determination	2	2	HANDHELD SPEED CONTROLLER	Energy control	2 controllers	Energy control
PBS x FBS	06/10/25	PBS	FBS	MATRIX	14	Adherence	Adherence on road	2	2	PNEUMATICS	Stability through adhesion	#	Stability through adhesion
PBS x FBS	06/10/25	PBS	FBS	MATRIX	31	Distribution on roads	Distribution	2	2	ELECTRICAL STRIPS	Energy distribution	2*6 meters (including bridge)	Energy distribution
PBS x FBS	06/10/25	PBS	FBS	MATRIX	31	Guidance	Guidance	2	2	ELECTRICAL STRIPS	Direction control	2*6 meters (including bridge)	Direction control
PBS x FBS	06/10/25	PBS	FBS	MATRIX	11	Motorisation	Movement transmission	2	2	MOTOR	Mobility on roads	#	Mobility on roads
PBS x FBS	06/10/25	PBS	FBS	MATRIX	1	Mobility	Movement	1	1	CARS	Mobility function	2 cars	Mobility function

TBS x WP	12/10/25	TBS	WP	MATRIX	MS	CON-PM	Consortium level	1	0	Contract master schedule	CON Project management (only workload = free)	Contractual target	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS01	CON-PM	Consortium level	2	0	Contract signature	CON Project management (only workload = free)	T0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS02	CON-PM	Consortium level	2	0	Monthly report	CON Project management (only workload = free)	Every 30 days	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS03	CON-PM	Consortium level	2	0	Delivery	CON Project management (only workload = free)	T0 + 89 days.	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS04	EM-EN	EM level	2	0	Commissioning	EM Engineering (only workload = free)	T0 + 85-89 days.	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS05	EM-EN	EM level	2	0	Acceptance	EM Engineering (only workload = free)	T0 + 90 days.	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS06	CON-PM	Consortium level	2	0	Warranty period	CON Project management (only workload = free)	1 year after acceptance date.	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS	CON-PM	Consortium level	1	0	Project master schedule	CON Project management (only workload = free)	Physical progress	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M	CON-PM	Consortium level	2	0	Milestones	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M01	CON-PM	Consortium level	3	0	Project charter issue	CON Project management (only workload = free)	1	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M02	CON-PM	Consortium level	3	0	Assignment of the core team	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M03	CON-PM	Consortium level	3	0	Consortium launch meeting	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M04	CON-PM	Consortium level	3	0	Project consortium management plan first issue	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M05	EM-EN	EM level	3	0	Development management plan first issue	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M06	CW-EN	CW level	3	0	Interface management plan first issue	CW Engineering (only workload)	0	CW Engineering (only workload)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M07	CW-EN	CW level	3	0	Production/installation management plan first issue	CW Engineering (only workload)	0	CW Engineering (only workload)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M08	EM-EN	EM level	3	0	Testing/commissioning management plan first issue	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M09	CON-PM	Consortium level	3	0	Progress meeting	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M10	CON-PM	Consortium level	3	0	Design frozen	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M11	CON-PM	Consortium level	3	0	Sourcing completed	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M12	CW-BLD	CW level	3	0	End of building installation	CW buildings	0	CW buildings
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M13	CW-BRO	CW level	3	0	End of roads installation	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M14	EM-PSTR	EM level	3	0	End of track installation	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M15	EM-CAR	EM level	3	0	Delivery of all cars	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M16	EM-PSTR	EM level	3	0	Delivery of all PS equipments	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M17	EM-EN	EM level	3	0	End of integration test	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M18	EM-EN	EM level	3	0	End of pre-commissioning	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M19	EM-EN	EM level	3	0	End of commissioning	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M20	CON-PM	Consortium level	3	0	Client acceptance date	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-M21	CON-PM	Consortium level	3	0	Invoices	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P	CON-PM	Consortium level	2	0	Phases	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P01	CON-PM	Consortium level	3	0	Launch	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P02	CON-PM	Consortium level	3	0	Design	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P03	CON-PM	Consortium level	3	0	Sourcing	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P04	CON-PM	Consortium level	3	0	Production/installation	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P05	CON-PM	Consortium level	3	0	Testing	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P06	EM-EN	EM level	3	0	Pre-commissioning	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P07	EM-EN	EM level	3	0	Commissioning	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P08	CON-PM	Consortium level	3	0	Acceptance	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	PMS-P09	CON-PM	Consortium level	3	0	Warranty	CON Project management (only workload = free)	0	CON Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-CW	CW-PM	CW level	1	0	CW group master schedule	CW Project management (only workload = free)	For CW project management	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-CW-M	CW-PM	CW level	2	0	CW Milestones	CW Project management (only workload = free)	Showing the interface milestones with EM	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-CW-M01	CW-PM	CW level	3	0	Project CW group management plan first issue	CW Project management (only workload = free)	0	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-CW-M02	CW-PM	CW level	3	0	CW latest installation	CW Project management (only workload = free)	0	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-CW-WBS	CW-PM	CW level	2	0	CW WBS schedule	CW Project management (only workload = free)	For CW task management	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	CW-(@-@)-M	CW-PM	CW level	3	0	CW project management	CW Project management (only workload = free)	0	CW Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	CW-(@-@)-D	CW-EN	CW level	3	0	CW engineering	CW Engineering (only workload)	0	CW Engineering (only workload)
TBS x WP	12/10/25	TBS	WP	MATRIX	CWB-(41-GB)-M	CW-BLD	CW level	3	0	Building management	CW buildings	0	CW buildings
TBS x WP	12/10/25	TBS	WP	MATRIX	CWB-(41-GB)-D	CW-BLD	CW level	3	0	Building design	CW buildings	0	CW buildings
TBS x WP	12/10/25	TBS	WP	MATRIX	CWB-(41-GB)-S	CW-BLD	CW level	3	0	Building supply chain	CW buildings	0	CW buildings
TBS x WP	12/10/25	TBS	WP	MATRIX	CWB-(41-GB)-I	CW-BLD	CW level	3	0	Building installation	CW buildings	0	CW buildings
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR1-(51-SR)-M	CW-BRO	CW level	3	0	Straight road management	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR1-(51-SR)-D	CW-BRO	CW level	3	0	Straight road design	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR1-(51-SR)-S	CW-BRO	CW level	3	0	Straight road supply chain	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR1-(51-SR)-I	CW-BRO	CW level	3	0	Straight road installation	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR2-(52-CR)-M	CW-BRO	CW level	3	0	Curve road management	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR2-(52-CR)-D	CW-BRO	CW level	3	0	Curve road design	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR2-(52-CR)-S	CW-BRO	CW level	3	0	Curve road supply chain	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR2-(52-CR)-I	CW-BRO	CW level	3	0	Curve road installation	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR3-(6-BR01)-M	CW-BRO	CW level	3	0	Bridge management	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR3-(6-BR01)-D	CW-BRO	CW level	3	0	Bridge design	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR3-(6-BR01)-S	CW-BRO	CW level	3	0	Bridge supply chain	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	CWR3-(6-BR01)-I	CW-BRO	CW level	3	0	Bridge installation	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	DAI-(@2-#)-D	CW-EN	CW level	3	0	Writing the assembly instructions	CW Engineering (only workload)	0	CW Engineering (only workload)
TBS x WP	12/10/25	TBS	WP	MATRIX	SPCR-(532-CR)-P	CW-BRO	CW level	3	0	Delivery of curve road spare parts	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	SPSR-(531-SR)-P	CW-BRO	CW level	3	0	Delivery of straight road spare parts	CW Road and bridge	0	CW Road and bridge
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-EM	EM-PM	EM level	1	0	EM group master schedule	EM Project management (only workload = free)	For EM project management	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-EM-M	EM-PM	EM level	2	0	EM Milestones	EM Project management (only workload = free)	Showing the interface milestones with CW	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-EM-M01	EM-PM	EM level	3	0	Project EM group management plan first issue	EM Project management (only workload = free)	0	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-EM-M02	EM-PM	EM level	3	0	EM latest production	EM Project management (only workload = free)	0	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	MS-EM-WBS	EM-PM	EM level	2	0	EM WBS schedule	EM Project management (only workload = free)	For EM task management	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	EME-(@-@)-M	EM-PM	EM level	3	0	E&M project management	EM Project management (only workload = free)	0	EM Project management (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	EME-(@-@)-D	EM-EN	EM level	3	0	E&M engineering	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-M	EM-CAR	EM level	3	0	Car management	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-D	EM-CAR	EM level	3	0	Car design	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-S	EM-CAR	EM level	3	0	Car supply chain	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-P	EM-CAR	EM level	3	0	Car production	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-T	EM-CAR	EM level	3	0	Car testing	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	CAR-(1-#)-C	EM-CAR	EM level	3	0	Car commissioning	EM Cars	0	EM Cars
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(2-PS)-M	EM-PSTR	EM level	3	0	Power supply management	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(2-PS)-D	EM-PSTR	EM level	3	0	Power supply design	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(2-PS)-S	EM-PSTR	EM level	3	0	Power supply supply chain	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	HSC-(21-PS)-P	EM-PSTR	EM level	3	0	Handheld speed controller production	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	HSC-(21-PS)-T	EM-PSTR	EM level	3	0	Handheld speed controller testing	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	HSC-(21-PS)-C	EM-PSTR	EM level	3	0	Handheld speed controller commissioning	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(22-PS)-P	EM-PSTR	EM level	3	0	PS pack production	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(22-PS)-T	EM-PSTR	EM level	3	0	PS pack testing	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(22-PS)-C	EM-PSTR	EM level	3	0	PS pack commissioning	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(23-PS)-P	EM-PSTR	EM level	3	0	PS cables production	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(23-PS)-T	EM-PSTR	EM level	3	0	PS cables testing	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-M	EM-PSTR	EM level	3	0	Track management	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-D	EM-PSTR	EM level	3	0	Track design	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-S	EM-PSTR	EM level	3	0	Track supply chain	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-I	EM-PSTR	EM level	3	0	Track installation	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-T	EM-PSTR	EM level	3	0	Track testing	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	PS-(3-@)-C	EM-PSTR	EM level	3	0	Track commissioning	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	ENG-(@-@)-C	EM-EN	EM level	3	0	Project commissioning	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	DUM-(@1-#)-D	EM-EN	EM level	3	0	Writing the user manual	EM Engineering (only workload = free)	0	EM Engineering (only workload = free)
TBS x WP	12/10/25	TBS	WP	MATRIX	SPSC-(241-PS)-P	EM-PSTR	EM level	3	0	Delivery of handheld speed controller spare parts	EM Power supply and tracks	0	EM Power supply and tracks
TBS x WP	12/10/25	TBS	WP	MATRIX	SPMO-(151-#)-S	EM-CAR	EM level	3	0	Delivery of motor spare parts	EM Cars	0	EM Cars